The proposed plan for the Reading Program in Hubli and Dharwad Rural: 09.

| Sl.no | Particulars | Time line | Venue |
| --- | --- | --- | --- |
| 1. | Permission from DDPI | 10-12-09 | - |
| 2. | Discussion with Hubli and Dharwad BEO’s and selection of the RPS (The RPs who had already trained in Reading Pro) | 11-12-09 | - |
| 3. | Refresh training for the RPs with Akshara Team | 15-12-09 | Akshara Office Dharwad |
| 4 | Training to 245 teachers in seven batches. (35X7=245) | 22-12-09 | In Govt. schools or BRC or CRC etc.. |
| 5 | Training to 245 teachers in seven batches. (35X7=245) | 23-12-09 | In Govt. Schools or BRC or CRC etc.. |
| 6. | The Baseline evaluation will be conducted as soon as the training gets over. And will be handed over to Akshara by the CRPs. | 28-12-09 | - |
| 7. | Program launch | 29-12-09 | - |
| 8 | Child wise data entry | 1st week of Jan-10 |  |
| 9 | Final evaluation | 18-2-2010 | - |

Working days for reading program:

| Sl.no | Months | Working days | Holidays |
| --- | --- | --- | --- |
| 1. | December-09 | 3 | - |
| 2. | January-10 | 19 | Makara Sankrnthi-1 Republic day-1 All the Saturdays-4 |
| 3 | February | 20 | Census -4 Saturdays-4 |
| 4 | Total no of working days | 42 |

Dharwad

| Sl.no | Name of the clusters | No. of Schools |
| --- | --- | --- |
| 1 | Heballi | 08 |
| 2 | Ameenbavi | 14 |
| 3 | Allavar Kannada | 21 |
| 4 | Allavar Urdu | 13 |
| 5 | Narendra | 13 |
| 6 | Tegur | 13 |
| 7 | Uppin Betageri | 13 |
| 8 | Honnapur | 15 |
| 9 | Mugad | 17 |
| 10 | Nigadi | 14 |
| 11 | Navloor | 13 |
| 12 | P.H Q Kannada Dharwad | 10 |
| 13 | P.H Q Urdu Dharwad | 16 |
|  |  | 180 |

Hubli

| Sl.no | Name of the clusters | No of schools |
| --- | --- | --- |
| 1. | Sirguppi | 15 |
| 2. | Noolvi | 13 |
| 3. | Rayanal | 14 |
| 4. | Arlikatti | 17 |
| 5 | Byahatti | 15 |
| 6 | Navangar Kannada | 10 |
| 7 | Navanagar | 11 |
| 8 | Bhairi Devarakoopa | 10 |
| 9 | Gabbur | 13 |
|  |  | 118 |

The total number schools in Hubli and Dharwad -298.The total no. of students: 74500

No. students identified for Remedial teaching for the academic year 2009-10 is: 13000(17% of the total children)

No. cards used for the reading program: 1 to 40.

Evaluations during the program:

- The baseline and the final evaluation.

- 2% third party evaluation.

Coordinators:

The total number of clusters in Hubli Dharwad Rural block is 22.

Number of Coordinators required: 11 (Two clusters per coordinator)