Memorandum of Understanding

Objective: To establish a strategic partnership between REAP Benefit Foundation(hereinafter known as “REAP Benefit”) and SELCO Foundation for the purpose of working on Waste-Water and Sanitation solutions in Government and low income schools in Karnataka.

REAP Benefit Foundation

REAP Benefit is a hybrid social enterprise founded in the year 2012 & registered in 2013. Reap Benefit, works with a mission to solve local environment & civic problems with young people in school, colleges & community. Reap Benefit believes in solving local problems with young people through local data, local customizable solutions & engaging the local stakeholders.

Reap Benefit Foundation has a specific focus to improve local environment & civic issues, like sanitation, water, waste, energy etc. which will directly-indirectly influences learning outcomes, attendance, better health & hygiene & above all developing important skills of problem solving, critical thinking, hands on problem solving amongst others.

SELCO Foundation

SELCO Foundation was founded in 2010. Since its inception, SELCO Foundation has expanded to create a holistic ecosystem to provide reliable energy services, for the benefit of impoverished segments in society. The Foundation works to link the benefits of sustainable energy to poverty eradication by collaborating with NGOs, local financial institutions, education institutions and social enterprises. SELCO Foundation envisions a socially sustainable society and seeks to create avenues for asset building, enhancement in quality of life and wealth creation that will uplift deprived sections of society through sustainable development solutions.

The solution framework adopted by SELCO Foundation is to create a network of research and development Labs which are an open source initiative capable of bringing social innovations to scale. The Foundation will be an anchor body that is open source and thus play a pivotal role in catalyzing innovative and replicable processes of tailored sustainable energy solutions via a bottom top approach.

Purpose of Memorandum of Understanding (MOU)

Nearly 200 million school-days are lost every due to inadequate waste-water-sanitation facilities.

In addition, most schools are without sanitation facilities of functional facilities like access to water or dumping of garbage. There is no toilet block set aside for girls, parents often won’t allow their daughters to attend school. This fuels the discrepancy in primary school completion rates: one in four girls do not complete primary school, compared to one in seven boys. Just improving sanitation facilities or building toilets and providing water purifers etc; is not the remedy to the solution. Forming consistent behaviours and attitudes is one of the primary objectives of an effective school  sanitation-health programme. It is important that children know about risks to their health and how to avoid these.

We hope to in partnership create a replicable model within the expanse to provide effective facilities, solutions and education to children through this programme.

Therefore this Memorandum of Understanding (“MOU”) is made on this 1 April 2016 between:

REAP Benefit Foundation(First Party)

#30,Church Road

Shantinagar

Bangalore 560027

AND

SELCO Foundation (Second Party)

#690, 15th Cross

2nd Phase, J P Nagar

Bangalore  560078, India

- PERIOD:

This MOU is valid for a period of six months, from 1 April 2016 to 1 April 2017 and can be renewed if both parties are agreeable to the terms and conditions as are negotiated at that time.

- SCOPE:

REAP Benefit and SELCO Foundation partner under this MoU to enhance the learning opportunities for the children at the selected schools in Karnataka. REAP Benefit, the operational and community partner, has established and is implementing the education centre, while SELCO Foundation will serve as the technology and knowledge partner and will look at bridging ecosystem gaps that will ensure better quality education in the community.

- ROLES & RESPONSIBILITIES OF REAP Benefit

- Collect local data about the schools

- Engage in the analysis of data collected

- Co-develop local solutions with the students

- Deploy and implement solutions in the schools

- Engage with the local communities

- Deliver on the project deadlines within the given timelines(refer Annexure)

- Monitor and collect data about the impact

- Serve as communication channel to ASHA and send regular updates

- ROLES & RESPONSIBILITIES OF SELCO FOUNDATION:

- Take the grant from ASHA For Education Stanford

- Coordinate the project activities

- Serve as communication channel to ASHA and send regular updates

- Support with ideation and system design

- Provide periodic feedback on the design and usability of the solutions

- Suggest schools for interventions

- Study the effectiveness of the deployed solution through regular observations.

- Identify the other interventions required to improve the programme

  - OTHER TERMS & CONDITIONS:

- This MOU shall contain the entire agreement of the parties. It may not be changed orally, but only by agreement in writing signed by both parties.

- Notwithstanding anything to the contrary in these Terms, it should be noted that SELCO Foundation provides support to its partners to enhance their chances to provide quality service to the poor. SELCO Foundation’s sole intent is to create a service by way of sustainable technical, financial and operational solution. SELCO Foundation will not and cannot be held responsible for any conflicts that may arise between GMRVF and its partners/users of their services during this program. However SELCO Foundation will make every attempt to resolve such conflicts to the best of its ability and in the interest of all parties.

7.  CONFIDENTIALITY:

SELCO Foundation and REAP Benefit will ensure that all information shared by each other is kept confidential and not disclosed to any third party. Such information shall only be disclosed to its employees/associates as may be required to provide the amenities as understood in this MOU.

8.  TERMINATION:

Either SELCO Foundation or REAP Benefit may terminate this MOU without cause, by thirty (30) days’ prior notice in writing, by either email or registered AD post.The possession of the projector will stay with SELCO Foundation.However it is understood that both parties will make every attempt to resolve differences amicably before taking such action.

9.  ANNEXURE:

| BUDGET |
| --- |
| Component | Cost (INR) |
| Total materials | 9,85,250 |
| Facilitator (2 years) | 7,72,000 |
| Designer (6 months) | 90,000 |
| Total | 17,95,250 |

| MONITORING PLAN |
| --- |
| TIME | RESOURCES/INPUTS | ACTIVITY/ ACTIONS | OUTPUT | OUTCOME/IMPACT |
| Y1Q1 (Jun – Sep 2016) | HR - Facilitator and Designer | Collect data from 15 Schools | Understand the market Baseline Data Collected | Baseline data helps understand what the needs of the stakeholders are and plan interventions in the next quarter |
|  |  | Designer: Rapid Prototype with 2 schools | Prototypes and Kits built | Ready to deploy solutions |
|  |  | Build solutions in numbers needed | Built solutions kept ready for deployment as Completely Knocked Down (CKD) Kits | Prepared to roll out plans for next quarter |
|  |  | Start Deployment of solutions |  |  |
| Y1Q2 (Oct – Dec 2016) | Kits (Waste, Water, Sanitation) | Deploy with 10 Schools | Stakeholders see the need for the solutions through the Kits Having used the Kits, they are prepared to adopt their usage habits around the new interventions | Behavior change process initiated through the use of Kits |
|  | Solutions (Waste, Grey Water, Sanitation) | Deploy with 10 Schools | Solutions implemented in the areas of Waste, Water, Sanitation | Solutions to support the behavior change process is put into place at 10 schools |
|  |  | Reward partners identified | Reward partners identified | Ready for next quarters plans |
| Y1Q3 (Jan - Mar 2017) | Monitoring and Evaluation framework | Collect data from 10 schools on usage of solutions and behavior around them | Analyzable data about post implementation of solutions and kits | Data for Analysis |
|  | HR - Facilitator and Designer | Analyze Data from these schools | Data analysis reveals trends in behavior change and adoption of solutions | Validation of solutions and identification of need to change either solutions or stakeholder engagement method |
|  |  | Implement rewards from Reward partners | 10 schools which have bought in |  |
| Y1Q4 (Apr - Jun 2017) | HR - Facilitator and Designer | Redesign stakeholder engagement and solutions if needed | Updated stakeholder engagement content and solutions | Ready for implementation in 5 schools and re-engagement in 10 schools from previous year |
|  |  | Deploy new content/solutions in 10 old schools and 5 new schools | Begin intervention in 5 new schools and reengage students in 10 old schools |  |
| Y2Q1 (Jul - Sep 2017) | HR - Facilitator and Designer | Deploy new content/solutions in 10 old schools and 5 new schools | Begin intervention in 5 new schools and reengage students in 10 old schools | All schools on same page with solutions being deployed in all of them |
|  | Solutions (Waste, Grey Water, Sanitation) |  |  |  |
| Y2Q2 (Oct - Dec 2017) | Monitoring and Evaluation framework | Collect data from 10 schools on usage of solutions and behavior around them | Analyzable data about post implementation of solutions and kits | Data for Analysis |
|  | HR - Facilitator and Designer | Analyze Data from these schools | Data analysis reveals trends in behavior change and adoption of solutions | Validation of solutions and identification of need to change either solutions or stakeholder engagement method |
| Y2Q3 (Jan- Mar 2018) | HR - Facilitator and Designer | Make Report |  |  |
|  | Reward partners | Implement rewards from Reward partners | 10 schools which have bought in |  |
| Y2Q4 (Jan- Mar 2018) | ?????? |  |  |  |

| TIMELINES FOR THE PROJECT |  |  |
| --- | --- | --- |
| MONTHS FROM LAUNCH | KEY MILE STONE | KEY MILE STONE | KEY MILE STONE | KEY MILE STONE | KEY MILE STONE | KEY MILE STONE |
| Project Deliverables | Facilitator | Designer | Sanitation System | Grey Water System | Waste Management | Rewards And Incentives |
| Mar-16 | Shortlist Applicants |  |  |  |  |  |
| Apr-16 | Finalize and Hire positions |  |  |  |  |  |
| May-16 | Training |  |  |  |  |  |
| June-16 LAUNCH (Month 0) | Exposure to schools and Expectation mapping of stakeholders and understanding barriers (15 schools) |  |  |  |  |
| July-16 | Understand Data Collection Tools | Ideation of solutions and planning, based on data collected |  |  |  |  |
| Aug-16 | Data collection + Ice breaking with students | Rapid Prototype + Build solutions and kits | Analyze: Pre intervention data is collected | Analyze: Pre intervention data is collected | Analyze: Pre intervention data is collected | Data collection + Ice breaking with students |
| Sept-16 | Data collection ( 15 schools) + Engagement with students of 10 schools about interventions in the year ahead | Deploy solutions (test schools - 2 numbers) | Engage the students about the intervention | Engage the students about the intervention | Engage the students about the intervention |  |
| Oct-16 | Plan interventions and engagement program | Collect data from deployments of solutions |  |  |  | Identify Reward Partners |
| Nov-16 | Deploy Solutions and engagement program (10 schools) | Redesign solutions, if needed + design communication material for the schools | Implementing solutions | Implementing solutions | Implementing solutions | Identify Reward Partners |
| Dec-16 | Deploy Solutions and engagement program (10 schools) |  | Implementing solutions | Implementing solutions | Implementing solutions | Identify Reward Partners |
| Jan-17 | Monitor and collect data on impact |  | Monitor and collect data on impact | Monitor and collect data on impact | Monitor and collect data on impact | Reward Schools |
| Feb-17 | Monitor and collect data on impact |  | Monitor and collect data on impact | Monitor and collect data on impact | Monitor and collect data on impact | Reward Schools |
| Mar-17 | Analyze Data collected |  | Analyze Data collected | Analyze Data collected | Analyze Data collected |  |
| Apr-17 | Retraining + Redesign solutions if needed |  | Redesign solutions/Maintenance support if needed | Redesign solutions/Maintenance support if needed | Redesign solutions/Maintenance support if needed |  |
| May-17 | Prepare for Round 2 of engagement |  |  |  |  |  |
| Jun-17 | Deploy Solutions and engagement program (5 schools new and reengage students of 10 old schools through reward based financing) |  | Implementing solutions | Implementing solutions | Implementing solutions |  |
| Jul-17 | Deploy Solutions and engagement program (5 schools new and reengage students of 10 old schools through reward based financing) |  | Implementing solutions | Implementing solutions | Implementing solutions |  |
| Aug-17 | Deploy Solutions and engagement program (5 schools new and reengage students of 10 old schools through reward based financing) |  | Implementing solutions | Implementing solutions | Implementing solutions |  |
| Sep-17 | Deploy Solutions and engagement program (5 schools new and reengage students of 10 old schools through reward based financing) |  | Monitor and collect data on impact | Monitor and collect data on impact | Monitor and collect data on impact | Deploy Solutions and engagement program (5 schools new and reengage students of 10 old schools through reward based financing) |
| Oct-17 | Monitor and collect data on impact in all schools |  | Monitor and collect data on impact | Monitor and collect data on impact | Monitor and collect data on impact | Identify Reward Partners |
| Nov-17 | Monitor and collect data on impact |  | Redesign solutions if needed | Redesign solutions if needed | Redesign solutions if needed | Reward Schools |
| Dec-17 | Analyze Data collected |  |  |  |  | Reward Schools |
| Jan-18 | Evaluating impact + Reward Based financing for the new 5 schools + Report Making |  |  |  |  |  |
| Feb-18 | Evaluating impact + Reward Based financing for the new 5 schools + Report Making |  |  |  |  |  |
| Mar-18 | Evaluating impact + Reward Based financing for the new 5 schools + Report Making |  |  |  |  |  |

For REAP Benefit		                                                   	For SELCO Foundation

___________________________________		___________________________________

Name:							Name:

Date:	Date: