# Sebama Foundation

(Social and Educational Body for Amenity and Mass Awareness)

Site Visit Report

Requested by

Minu Palani

Asha Colorado

Conducted by

N.Raj Jeba Durai

On September 20th & 21th, 2004

Dharmapuri District, Tamilnadu, India

N.Raj Jeba Durai holds an MA in public administration from Madras University and has been a volunteer of Asha in Chennai, India for over 2 and half years. He is deeply involved in over 10 diverse Asha projects and looks forward to site visits as exciting avenues to facilitate India-wide teamwork towards UQE.

I. Purpose of site-visit

II. Reaching Sebama

III. Answers to Minu’s questions regarding progress of construction work

IV. Segment-wise breakdown of construction proposed by Sebama to Asha Colorado

V. Summary

VI. Travel Expenses

I. Purpose of site-visit

In September - 2004, Asha Colorado volunteer Minu requested a second followup site visit to the Sebama Foundation. The purpose of the site visit was to collect details on the progress of the ongoing construction work.

II. Reaching Sebama

Traveling by bus, I left Chennai on Monday, Sept 20th night at 10:30 PM and reached Sebama Foundation on Tuesday, 21st Morning at 6.00AM. Brother Louis Rayan, founder & trustee of Sebama Foundation, welcomed me warmly.

III. Answers to Minu’s questions regarding progress of construction work

- What is the exact extent of work completed thus far?

The work completed so far include construction of 16 rooms including ground floor and first floor. Ramps are completed. In ground floor, plastering work is complete.  In first floor, brickwork for the roof is in progress.

- Does brother have any question to us, concerns etc?

Brother Louis Rayan, requests construction of toilets and bathrooms for the students.   These items were not included in the proposal before. The additional expenses this entails are:

COST OF DETAILS – TOILET, BATHROOM

- Earthwork excavation 	  		16.50m.cu x 150                  = 2,475

- Sand Filling                 	  		5.00m.cu x  400                   = 2000

- Raff Beam                    	  	             3m.sq   x  4500                   = 13,500

- B.W. 1; 6			 	           28m.cu x  1500	                    = 42,000

- Roof 			  	          6m.cu   x  5000                     =  30,000

- MS/RDS                              		2 MT x 32000                     =  64,000

- Plastering                               		302m.sq x 500                    =  15,100

- Flooring Concrete 1; 5; 10	    	7.63m.cu x 1,250                =  9,538

- Glass Tiles			  	           60m.sq x 500                       =   30,000

- Door                                    	  	6 x 2,000                            =   12,000

- Jolly LS                                                                    	 	       =   3,887

- Electrification                                                          		       =  12,500

- W/S 2 Sanitary, Bore well with Motor                        		       =   78,000

- W.W/C.W                                                                    		       = 10,000

Total         3,25,000

## ABSTRACT SEPTIC TANK

1.  Earthwork excavation		55m.cu x 150/m.cu		 = 8,250

2.  P.C.C   1; 5; 10                              320m.cu x 1250/m.cu              = 4000

3.  B.W. CM 1; 4 			13m.cu x 1600/m.cu		 = 20,800

4.  Plastering on 1; 4			50m.sq x 60/m.sq		 = 3000

5.  R.C.C 1; 2; 4			1.50m.cu x 4000/m.cu		 = 6000

6.  MS/RTS Steel Rods		175kgs x 32/kg                         = 5,600

- S.W. Pipe line

Ventilating Shaft

C.I Manhole cover etc and Dispresion Trench L.S                       = 27,350

Total      75,000

### RAMP WORK

1.  B.W. in c. M. 1;5       1x2     15.00 x 0.23 x 1.00 + 2.00 = 10.35m.cu    =  15,525

- 1,500

2.  P1. 1:5 12MM	    1x2x2   15.00x 1.00+2.00		= 90 M2	= 5,400

2		      60

3.  R.C.C. 1:2:4 raff beam 1x2    15.00x0.30x0.30		= 3.00M3	=13,500

400

4. Ms/Rts Steel Rods	     3M3x215 kg/m3			=650 Kg 	=20,800

32

5. Door 		       0.75x1.80 M		=2 Nos.x 2000 	= 4,000

6. Flooring with P.c.  1:5:10 1x1  15x1.80		= 27mM2x150/M2	 =4,050

7. Unforseen item found necessary during execution,

Painting, white washing, colour washing, iron grills  			 = 11,725

Total    Rs          75,000

3.  When we anticipate completion?

The work will be completed before 31st December 2004 depending upon funds availability.

4. Have there been any changes to the initial plan?

According to the initial proposal, we planned for 20 rooms of width 20/16.  But it has been changed to 16 rooms of width 20/20. The reason for change in the plan is to make the rooms larger and comfortable to accommodate more children. Also the wooden door has been changed to steel door.

- Do you feel there is a need for a third party (architect) evaluation?

Through the visits, I found no need for a third party evaluation because the work in progress is good and the expense bills shown to me have been appropriate. If you strongly feel the need of a third party then we can do it also.

IV. Segment-wise breakdown of construction proposed by Sebama to Asha Colorado

IVa. Original Proposal

| Description of Work | Rs |
| --- | --- |
| 1st segment | 12500 |
| Earth work excavation | 210000 |
| Foundation Cement concrete in C.C 1:5:10 for foundation and flooring | 202500 |
| R.R Masonry in c.c 1:5 mix using HBG metal inclusing curing etc., complete |  |
|  | 425000 |
| 2nd segment | 1462500 |
| R.C.C Roof 1:2:4 using 15 mm HBG metal | 66000 |
| Weather course in roof slab in surki motor cm 1:3 with std specs. |  |
|  | 1528500 |
| 3rd segment |  |
| Brick work in c.m 1:5 using country bricks including cost and convenyance | 540000 |
| Plastering in all outer and inner surfaces Hd walls | 255000 |
|  | 795000 |
| 4th segment |  |
| Supplying and fixing of country wood doors and windows | 195000 |
| Flooring finishing pressed mosaic tile standard specs etc., complete | 132000 |
| White washing and outer washing | 68000 |
| Painting two coats for door and windows | 37500 |
| Provision for electrification arrangements | 66000 |
| Provision for water supply arrangements | 20000 |
| Other items | 20000 |
| Provision for decorative arrangements | 7500 |
| Provision for unforseen arrangements | 5500 |
|  | 356500 |
| Total | 3300000 |

IVb. Timeline

The second site visit confirms completion of segments 1, 2

| Description of Work | Rs |
| --- | --- |
| 1st segment | 12500 |
| Earth work excavation | 210000 |
| Foundation Cement concrete in C.C 1:5:10 for foundation and flooring | 202500 |
| R.R Masonry in c.c 1:5 mix using HBG metal inclusing curing etc., complete |  |
|  | 425000 |
| 2nd segment | 1462500 |
| R.C.C Roof 1:2:4 using 15 mm HBG metal | 66000 |
| Weather course in roof slab in surki motor cm 1:3 with std specs. |  |
|  | 1528500 |

The amount received for the construction work (1st and 2nd segment) Rs. 19,53,500.  The bills produced to Jeba were Rs. 19,63,630 during the Sept 20th/21st site-visit.

| 3rd segment |  |
| --- | --- |
| Brick work in c.m 1:5 using country bricks including cost and convenyance | 540000 |
| Plastering in all outer and inner surfaces Hd walls | 255000 |
|  | 795000 |

Funding for 3rd segment completion needed before end of October

| 4th segment |  |
| --- | --- |
| Supplying and fixing of country wood doors and windows | 195000 |
| Flooring finishing pressed mosaic tile standard specs etc., complete | 132000 |
| White washing and outer washing | 68000 |
| Painting two coats for door and windows | 37500 |
| Provision for electrification arrangements | 66000 |
| Provision for water supply arrangements | 20000 |
| Other items | 20000 |
| Provision for decorative arrangements | 7500 |
| Provision for unforseen arrangements | 5500 |
|  | 356500 |
| Total | 3300000 |

Funding for 4th segment completion needed before end of November.

If the funds reach on time, the construction will be completed as I mentioned before i.e., before 31st December 2004.

V. Summary

1. The construction is progressing nicely more or less per the original plan. I have seen all the bills and they are appropriate. I have spoken to the engineer Mr.Sathivel (mobile number 9443267308) and discussed the construction plan. I am satisfied with the work going on in Sebama foundation.

2. I will mail the MOU form within one week.

3. I had a good chance to meet all the students once again. It’s really a wonderful experience for me to meet all the students and know they are very happy about the upcoming building.

4. We can have a third site visit scheduled during the first week of December  because most probably all the work will be complete by then.

VI. Travel Expenses

Rs

1. Tickets to Dharamapuri and back to Chennai			400

2. Food  								200

3. Auto fare to reach Sebama						70

4. Auto fare to reach bus stand in Chennai				100

5. Auto fare from bus stand to home					100

6. Internet to prepare report 						50

Total			920 ( $21)

[Note - I had to use auto as I reached Dharamapuri at early morning 4.00 AM and Chennai at early morning 4.30 AM]