ASHA WORK REPORT AS ON MARCH 2002 TO MAY 2002

Reported to:

Subasiri Rao

Asha Colorado

USA.

1.	I am your primary contact for Asha Stars, Asha CO and Sonaimuthu. Any communication needs to be done only through me.

We will follow your guidance and made contacts through by you. We have received some CC references in emails. Hence we also made CC  to Mrs.Priya, Mr.Subbu and all. We assured to follow your guidance to implementing our project.

2. We would like a progress report of how you have utilized the funds for this current 3-month funding period?

At present 339 rural hill areas children are studying in our 10  supplementary education centers.

Village wise details:

| S.N | Villages | Students Strength | Teacher responsible |
| --- | --- | --- | --- |
| 1 | Puduppatti | 30 | Mrs. R.Vishalatshi |
| 2 | Kipiapuram | 40 | Miss Alagunachi |
| 3 | Chinnamalaiyur | 32 | Mr.Sivalingam |
| 4 | Chinnayapuram | 35 | Mrs.Tamilselvi |
| 5 | Uralipatti | 28 | Mr.Palaniammal |
| 6 | Kannamanoor | 30 | Mrs.Gheetha |
| 7 | Merkupatti | 32 | Miss. Usharani |
| 8 | Musukkampatti | 34 | Mrs. Ponmani |
| 9 | Kalathupatti | 38 | Mrs.Palaniammal |
| 10 | Serveedu | 40 | Miss. Hemavathi |
|  | Total | 339 |  |

Fund Utilization statement for 3 months from March 2002 to May 2002

Income			Amount (Rs.)	Expenditure			Amount (Rs.)

To Grant received from 			1. Tuition Centre Maintenance

Asha – USA		22,250.00	Education Material Expense

(443 $)					(Rs.300 X 10 Centres)			3,000.00

Teacher Salary

(Rs.300 X 10 X 3 months)		9,000.00

Room Rent and Electricity

(Rs.100 X 10 X 3 months)		3,000.00

2. Supervisor Salary

(Rs.750  X 1 X 3 months)		2,250,00

3. Teacher Training Expense	5,000.00

________						________

22,250.00						22,250.00

________						_________

Our community people and Women SHGs people are arranged accommodation to this centre. Local Panchayat Raj members and SHGs are involving monitoring and regularizing our school activities. Always all school students started with Tamil Thai Valthu and ended with National Anthem. In between our teachers are guiding the children to studying well, regularizing home works, play way method education, joyful learning and singing songs. Our strategies minimizing illiterate family burden by strengthening education, preventing dropout’s rates, Truancy, Vagrancy and child labour in the project villages. To strengthen the teacher’s knowledge we have conducted teachers training at Annapanni Pudukottai. We have invited experts from DIET training centres and children conduct this training programme.  we put the Boards at all 10 schools in the style of Asha Colorado – SAADOW Supplementary centre in this project villages.

3. We would also like you to send us your objectives for the next 3 months.

Objectives:

- Maximise the children education rate by preventing school dropouts and child labours in the hilly area project villages.

- Create interest on child education by adopting plyway and joyful learning approaches. And further make easy their education.

- Prevent female gender biased education system in the project area.

- Reducing illiterate family burden by providing supplementary education

- Providing quality education and improve the standard of education among hilly areas children.

Next 3 months Budget:

Items						Amount (Rs.)

1. Tutition Centre Maintenance

Education materials (Rs.300 X 10)				  3,000.00

Teacher Salary (Rs.500 X 10 X 3 )				15,000.00

Room rent & Electricity (Rs.200 X 10 X 3)			  6,000.00

2. Supervisor Salary (Rs.1000 X 1 X 3)			  3,000.00

3. Contingency						  2,000.00

_________

Total					29,000.00

_________

Therefore One Dollar is equal to Rs.49/-

Rs.29,000.00 is equal to 592 Dollars. (Five Hundred and Ninety two Dollars only)

ii) If you can break down your objectives for 3 month intervals for the next one year.

Next years onwards we have take additional 5 centres in 5 villages.

For the First 3 months: (March 2003 to May 2003)

1.Tuition Centre Maintenance:					Amount (Rs.)

Educational Materials (Rs.500 X 15 )				   7,500.00

Teacher Salary (Rs.500 X 15 X 3)				 	 22,500.00

Room rent and Electricity (Rs.200 X 15 X 3)			   9,000.00

2. Supervisor Salary (Rs.1200 X 1 X 3)				   3,600.00

3. Teacher Training Expense					   7,000.00

4. Contingency							   3,000.00

_________

Total						52,600.00

_________

Therefore One Dollars is equal to Rs.49/-

Rs.52, 600/- is equal to 1074 Dollars. (One thousand and Seventy four only)

II For the Second 3 months: (June 2003 to August 2003)

1.Tuition centre maintenance:

Teacher salary (Rs.500 X 15 X 3 )					22,500.00

Room rent, Electricity (Rs.200 X 15 X 3)			 	  9,000.00

2. Supervisor salary  (Rs.1200 X 1 X 3)				  3,600.00

3. Contingency							  2,000.00

________

Total						37,100.00

________

Therefore One Dollar is equal to Rs.49/-

Rs.37,100/- is equal to 758 Dollars ( Seven Hundred and fifty eight  Dollars only)

III  For Third 3 months : (September 2003 to November 2003)

1. Tuition Centre Maintenance:

Educational Materials (Rs.500 X  15 )				  7,500.00

Teacher Salary (Rs.500 X 15 X 3)					22,500.00

Room rent & Electricity (200 X 15 X 3 )				  9,000.00

2. Supervisor Salary  (Rs.1200 X 1 X 3)				  3,600.00

3. Teacher training Expense						  7,000.00

4. Contingency							  3,000.00

________

Total					52600.00

________

Therefore One Dollar is equal to Rs.49/-

Rs.52 600/-is equal to 1074 Dollars (One thousand and Seventy four only)

IV  For the Fourth 3 months (December 2003 to February 2004)

1 Tuition Centre Maintenance:					Amount (Rs.)

Teacher Salary (Rs.500 X 15 X 3)	 				22,500.00

Room rent and Electricity (Rs.200 X 15 X 3)			  9,000.00

2. Supervisor Salary (Rs.1200 X 1 X 3 )				  3,600.00

3. Contingency							  2,000.00

_________

Total							37,100.00

_________

Therefore One Dollar is equal to Rs.49/-

Rs.37,100.00 is equal to 758 Dollars. (Seven Hundred and Fifty eight Dollars only)

4. Please provide a breakdown of fund utilization every quarter.

Fund Utilization statement for 3 months from March 2002 to May 2002

Income			Amount (Rs.)	Expenditure			Amount (Rs.)

To Grant received from 			1. Tuition Centre Maintenance

Asha – USA		22,250.00	Education Material Expense

(443 $)					(Rs.300 X 10 Centres)			3,000.00

Teacher Salary

(Rs.300 X 10 X 3 months)		9,000.00

Room Rent and Electricity

(Rs.100 X 10 X 3 months)		3,000.00

2. Supervisor Salary

(Rs.750  X 1 X 3 months)		2,250,00

3. Teacher Training Expense	5,000.00

________						________

22,250.00						22,250.00

________						_________