## Sheet1
SUSTAINABLE AGRICULTURE PROGRAMME FOR THREE YEARS.
| Activities | Budget | Budget | Budget
| Programme cost | Year I | Year 2 | Year 3
I | Assistance for purchase
1 | Purchase of land of 2 acres with registration charges. | 550000 | 0 | 0
2 | Fencing for land bundry | 30000 | 0 | 0
( Stone piller, bubbed wire including fixing charges )
3 | Water source | 100000 | 0 | 0
( Digging tube well and instalation of electric pump, pump house )
4 | Purchase of Agriculture equepments | 30000 | 5000 | 2500
( Mamty, Crobar, Pikacy, Butties, Weeder Machine etc., )
5 | Purchase of Cross breed Cows | 35000 | 5000 | 5000
(Rs. 15,000 x 2 cows) maintance cost.
6 | Construction of low cost cow shed ( 15' x 15' shed) | 25000 | 0 | 0
7 | Construction of One Bio-Gas Unit | 30000 | 0 | 0
( 210 Cmt Unit)
8 | Instalation of Solar Units for B.S centre
| - For lighting systems | 30000 | 0 | 0
| - For Water Heating system | 40000 | 0 | 0
9 | Bridge School Centre Construction | 400000 | 0 | 0
( 1 Hall, 1 Daining hall, 1 Kitchen room, 3 Bed rooms, 1 Store room, 1 Security room)
10 | Furniture and Fixtures (Tables, Food prepration vissels, almera, Chairs) | 30000 | 0 | 0
| Sub Total Rs. | 1300000 | 10000 | 7500
II | Land development activities.
1 | Promotion of Forestry seedlings (Fodder, fuel, timber yield sapplings) | 12500 | 0 | 0
( Rs.25 x 500 plants per year )
2 | Esableshment of Vermi Compost units | 24000 | 0 | 0
( Rs.12000 x 2 Units)
3 | Horticultue Development ( Plants, transportation and Pits)
| - Mango - 40 plants | 4500 | 0 | 0
| - Sapota - 40 plants | 4000 | 0 | 0
| - Coconut - 30 plants | 4000 | 0 | 0
| - Banana Plants - 300 | 15000 | 0 | 0
| - Arecnut Plants - 300 | 19500 | 0 | 0
4 | Concentrated organic manure preparation, Jeevamrutha | 5000 | 0 | 0
( Rs.5000 per year)
5 | Azolla development units | 2000 | 0 | 0
( Rs. 1000/unit x 2 units)
6 | Fodder grass seeds development | 5000 | 0 | 0
(maiz, hameta, NB-21, Congo signal, Guneia para, horsegrome etc)
7 | Bio-pesticides units | 5000 | 5000 | 2500
8 | Neem Oil. (100 leters x Rs.100/let) | 10000 | 5000 | 5000
9 | Neem cake and Pongemia cake ( Rs.10/kgs x 1500 kgs) | 15000 | 7500 | 5000
10 | Bee keeping unit (Box and extract machine) | 5000 | 0 | 0
11 | Farm ponds ( Rain water harvesting, Size 9mtr x 3mtr) | 10500 | 0 | 0
( Rs.10500 )
12 | Kitchen garden development (Vegetables, Drumstic etc ) | 2500 | 0 | 0
13 | Promotion of Fishing units | 5000
| Sub Total Rs. | 148500 | 17500 | 12500
V | Administration expenses.
1 | Communication (Postage, Fax, xerox etc ) (Rs.200 per month) | 2400 | 2400 | 2400
2 | Printing & Stationary ( Rs.100 per month) | 1200 | 1200 | 1200
3 | Documentation and reporting ( Rs.5000/year) | 5000 | 5000 | 5000
4 | Travel for Project Coordinator ( Rs. 600/month x 12 months) | 7200 | 7200 | 7200
5 | Telephone instalation ( Including internet) | 5000 | 2500 | 2500
6 | Miscellaneous expenses ( Rs.5000 per year ) | 5000 | 5000 | 5000
| Sub Total Rs. | 25800 | 23300 | 23300
VI | Hanorarium ( Personal cost )
1 | Project Coordinator - (Monitoring, account keeping) | 48000 | 52800 | 58080
( Rs.4000 x 12 months)
2 | Farm Maintenance Labour - 2 | 72000 | 79200 | 87120
( Rs.3000 x 12 x 2 laburs)
| Sub Total Rs. | 120000 | 132000 | 145200
CONSOLIDATED BUDGET
Sl | Item | Year 1 | Year 2 | Year 3
I | Assistance for purchase | 1300000 | 10000 | 7500
II. | Land development activities. | 148500 | 17500 | 12500
III | Administration expenses. | 25800 | 23300 | 23300
VI | Hanorarium ( Personal cost ) | 120000 | 132000 | 145200
| Grant Total Rs. | 1594300 | 182800 | 188500
| Organisation Contributuion. | 150000 | 22380 | 22700
| Grant request from ASHA for Education Rs. | 1444300 | 160420 | 165800
Note: This budget not includes Any Bridge Schools Components

## Sheet2
| Action Plan for three years |  |  |  |  | 2008-10
| Activities | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Programme cost
I | Assit purchasing
1 | Purchase of land of 2 acres with registration charges. | bar: 2008-10 May to 2008-10 Jun
2 | Fencing for land boundry | bar: 2008-10 Jun to 2008-10 Jul
( Stone piller, bubbed wire including fixing charges )
3 | Water source
( Digging tube well and instalation of electric pump, pump house ) | bar: 2008-10 Jun
4 | Purchase of Agriculture equepments | bar: 2008-10 Jun
( Mamty, Crobar, Pikacy, Butties, Weeder Machine etc., )
5 | Purchase of Milchy Cows ( Cross Brides) | bar: 2008-10 May to 2008-10 Jun
6 | Construction of cow shed ( 15' x 15' shed) | bar: 2008-10 May to 2008-10 Jun
7 | Construction of One Bio-Gas Unit | bar: 2008-10 Nov to 2008-10 Dec
( 210 Cmt Unit)
8 | Instalation of Solar Units for B.S centre
- For lighting systems | bar: 2008-10 Oct to 2008-10 Nov
- For Water Heating system | bar: 2008-10 Oct to 2008-10 Nov
9 | Bridge School Centre Construction
( 1 Hall, 1 Daing hall, 1 Kitchen room, 4 Bed rooms, 1 Store room) | bar: 2008-10 Nov to 2008-10 Dec
10 | Furniture and Fixtures ( Tables, Food prepration vissels, almera, Chairs) | bar: 2008-10 Nov to 2008-10 Dec
Sub Total Rs.
II | Land development activities.
1 | Promotion of Forestry seedlings (Fodder, fuel and timber yielding) | bar: 2008-10 May to 2008-10 Jun
2 | Esableshment of Vermi Compost units | bar: 2008-10 Jun to 2008-10 Jul
3 | Horticultue Development
- Mango - 40 plants | bar: 2008-10 May to 2008-10 Jul
- Sapota - 40 plants | bar: 2008-10 May to 2008-10 Jul
- Coconut - 30 plants | bar: 2008-10 May to 2008-10 Jul
- Banana Plants - 300 | bar: 2008-10 May to 2008-10 Jul
- Arecnut Plants - 300 | bar: 2008-10 May to 2008-10 Jul
4 | Concentrated organic manure preparation, Jeevamrutha | bar: 2008-10 May to 2008-10 Jul
5 | Azolla development units | bar: 2008-10 May to 2008-10 Jul
6 | Fodder grass seeds development | bar: 2008-10 May to 2008-10 Jul
(maiz, hameta, NB-21, Congo signal, ginea, horsegrome etc)
7 | Bio-pesticides unit | bar: 2008-10 May to 2008-10 Oct
8 | Neem Oil (100 leters x Rs.100/let)
9 | Neem cake and Pongemia cake ( Rs.10/kgs x 1500 kgs) | bar: 2008-10 Jun to 2008-10 Sep
10 | Bee keeping unit (Box and extract machine)
11 | Farm ponds ( Rain water harvesting, Size 9mtr x 3mtr) | bar: 2008-10 Jul to 2008-10 Aug
12 | Kitchen garden development (Vegetables, Drumstic etc ) | bar: 2008-10 Jun to 2008-10 Oct
13 | Documentation and monitoring