CLT INDIA

(Regd. as Children’s Lovecastles Trust)

The e-Patashale Program

Second Report: Mar 06 – July 06

Jakkur Village Post, Bangalore –560 064

Email Id: info@cltinda.org Website: www.cltindia.org

Ph: 080 56696702 / 28461949

Mar – Mid May 06 Summer Vacation –

Officially, the schools were closed. However, the CLT Learning Center was open for children for exploratory learning. Saturdays are open house for the teachers to sharpen their skills.

Mid May – Mid July 06

Operational areas so far

- Purnapura Government School

- Amrithahalli Government School

- Yelahanka New Town Government School

- Byatarayanapura Government School

- Srirampura Government School

- Jakkur Government School

- No. Of Schools – 6

- No. Of Teachers - 60

- No. Of Visits – 20 (I Phase) + 28 ( II Phase) per school

- No. Of hours – 2 hours per visit – 40 hrs approx. +  56 hrs approx ( II Phase)

Profiles of all teachers collected (form & scanned samples attached)

Topics taught at each school

*Refer curriculum attached

- Practical difficulties faced-

  - Lack of initiative from the Dept. of Education to mobilize teachers for a general training at the main center

  - Change of BEO (Block Education Officer)

  - Lack of electricity in Byatarayanapura Government school led to the delay in beginning the program

- Action taken to address the problems –

  - Several meetings with the BEO (Block Education Officer) to explain the value add-on of this program

  - Made clear to schools that computers will be installed only after they complete basic training at the center (minimum of 10 hours) & permission required for this should be acquired by the BEO on their own.

- Success stories-

  - Amazingly positive & enthusiastic response from the teachers of the government school

  - Byatarayanapura School finally opened up the doors of the CRC for the teachers.

  - Amrithahalli HM set up a separate computer lab for the purpose by mobilizing the School Betterment Committee

  - Trainee teachers have signed up come to be trained at the main center of their own initiative.

- Plan for next quarter

  - One workshop for all the teachers from 70 schools on best pedagogical practices

  - Build on e-content & sample projects

  - Prepare assignment worksheets for teachers

Beneficiaries

- E-Patashale Program – 6 Schools  mentioned above

- Workshop for teachers for best teaching practices -

Cluster Resource Centers                   No. of                          No. of

Schools                      Teachers

Byatarayanapura                                      33                                156

Yelahanka New Town                              18                                  80

Yelahanka Old Town                                19                                  80

TOTAL                70                                 316

Attachments

- Pictures

- Updated curriculum

- School visit timetable

- Program feedback format