## Sheet1
Updated 29 Oct 2005
| Expenses by categories | [19 empty] | INR
| Bank charges | 246 |  |  |  | 0.01737 | 0.61% of the total | [12 empty] | Funds raised for the project from various sources | 1416350
| Conveyance/Travel/ refreshment | 2281 |  |  |  | 0.16106 | [13 empty] | Total expenses January 2005 to October 2005 | -1416209
| Postage/ stationery and Xerox | 232 |  |  |  | 0.016382 | [13 empty] | Balance | 141
| Honorarium for services rendered | 5950 |  |  |  | 0.42014
| Student welfare | 1399321 |  |  |  | 98.8075 | 99.39% of the total
| Transportation of materials | 8179 |  |  |  | 0.57753
| Total expenses | 1416209
Items provided to children under back to School project
Item Nos
1 | Complete kit- School bag, drawing book, crayons/colours/paints (age appropriately) , pencil box (with pencils, eraser, sharpener & pens from Class 6 upwards), lunch box
2 | Notebooks as per requirment
3 | Clothes as per requirement
3A | 2 sets uniforms
3B | one set uniform & one set civil clothes
3C | one set civil clothes
3D | one set of uniforms
The followingTsunami affected places have given us lists of children and requested Asha Chennai to support
No.of children in each class
S. No | Place | LKG | UKG | Grade 1 | Grade 2 | Grade 3 | Grade 4 | Grade 5 | Grade 6 | Grade 7 | Grade 8 | Grade 9 | Grade 10 | Grade 11 | Grade 12 | College | Non Specific | Total | Status of the work | Details of support
1 | Nemmili Kuppam | 6 | 11 | 5 | 3 | 11 | 8 | 9 | 6 | 9 | 4 | 4 | 6 | 1 | 6 | 4 | 0 | 93 | completed and handed over to the children end January 2005 | Items 1,2, 3B
2 | Pattipulam 10 kms North of Mahabalipuram | 5 | 5 | 14 | 6 | 9 | 19 | 7 | 11 | 14 | 13 | 4 | 3 | 3 | 2 | 9 | 0 | 124 | Only civil clothes left, others handed over to children end Feb 2005 | Items 1,2, 3C
3 | Pudu Edaiyur 5 kms North of Mahabalipuram | 0 | 0 | 9 | 6 | 0 | 3 | 7 | 4 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 39 | Only civil clothes left, others handed over to children end Feb 2005 | Items 1,2, 3C
4 | Corporation Middle School, No1, V.R. Pillai street, Triplicane Chennai -5 (92 students) and 60 students of Llyods Road CPS( Zone 6) | 0 | 0 | 15 | 10 | 20 | 24 | 15 | 29 | 23 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | completed and handed over to the children | Items 1,2, 3A
5 | Corporation Primary School, Lock Nagar, Chepauk, Chennai -5( Zone 6) | 0 | 0 | 12 | 8 | 7 | 6 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | completed and handed over to the children | Items 1,2, 3A
No.of children in each class
S. No | Place | LKG | UKG | Grade 1 | Grade 2 | Grade 3 | Grade 4 | Grade 5 | Grade 6 | Grade 7 | Grade 8 | Grade 9 | Grade 10 | Grade 11 | Grade 12 | College | Non Specific | Total | Status of the work | Details of support
6 | Sirkazhi (Tirumullaivasal Village) | 68 | 72 | Grade 1: 84; Grade 2: 136; Grade 3: 119 |  | 21 | 500 | On the way to Sirkazhi, handed over by mid March2005 | Items 1, 3D for 479, and only Item 1 for 21 children of other than govt. schools
7 | Corporation Primary School, Tiruvanmiyur Kuppam, Zone 10 |  | Details of the boy / girl numbers awaited | [13 empty] | 0 | 100 | handed over by mid March2005 | Items 1, 3C/3D
8 | Shastri Nagar Mahalir Manram Day Care Centre |  | Details of the boy / girl numbers awaited | [13 empty] | 0 | 70 | handed over by mid March2005 | Items 1, 3C/3D
| More corporation schools in Zone 6, where some children have been partially affected by the Tsunami- Details below | [17 empty] | handed over by mid April 2005 | Items 1, 3C/3D
9 | CMS Begum Sahib St |  |  | Grade 1: 12; Grade 2: 12; Grade 3: 6; Grade 4: 6; Grade 5: 6; Grade 6: 6; Grade 7: 5 |  |  | 53 | Completed in April 2005
10 | CPS Llyods Road |  |  | Grade 1: 9; Grade 2: 10; Grade 3: 14; Grade 4: 11; Grade 5: 8 |  |  | 52 | Completed in April 2005
11 | CMS Big Street |  |  | Grade 6: 20 |  |  | 20 | Completed in April 2005
12 | CMS Ellispuram |  |  | Grade 1: 20 |  |  | 20 | Completed in April 2005
13 | CMS Thypoon Alikhan St |  |  | Grade 1: 25 |  |  | 25 | Completed in April 2005
14 | CMS TH Road |  |  | Grade 1: 20 |  |  | 20 | Completed in April 2005
15 | CMS Krishnampet |  |  | Grade 1: 40; Grade 2: 41 |  |  | 81 | Completed in April 2005
16 | CMS TP Koil St |  |  | Grade 1: 20 |  |  | 20 | Completed in April 2005
17 | CMS Balaji St |  |  | Grade 1: 20 |  |  | 20 | Completed in April 2005
18 | DayaGhar Third avenue Besant Nagar &Besant Nagar Club |  | 5 | 2 | 1 |  | 2 | 2 | 2 | 3 | 1 |  | 1 |  |  |  |  | 19 | Completed in Aug 2005
19 | Sinthanai Sirpi Akkarapettai | 57 | 47 | Grade 1: 36; Grade 2: 43; Grade 3: 33; Grade 4: 37; Grade 5: 17 |  |  | 270 | Completed in early July 2005 | Items 1 3A and footwear
Through UWF
20 | Singaravelan Nagr Cheenai13 |  |  | Grade 4: 2; Grade 5: 1; Grade 6: 3; Grade 8: 1; Grade 9: 2; Grade 10: 1 |  |  | 10 | Completed in June 2005 | Items 1,2,3A
21 | Nagoorar Thottam Chennai81 |  |  | Grade 1: 3; Grade 2: 4; Grade 3: 4; Grade 4: 5; Grade 5: 2; Grade 6: 1; Grade 8: 1 |  |  | 20 | Completed in June 2005 | Items 1,2,3A
22 | Thangammal st. Chennai-81 |  |  | Grade 4: 1; Grade 5: 1; Grade 6: 3; Grade 7: 2; Grade 8: 1; Grade 9: 1; Grade 11: 1 |  |  | 10 | Completed in June 2005 | Items 1,2,3A
23 | Durai st. Kasimedu- Chennai-81 |  |  | Grade 6: 2; Grade 7: 2; Grade 8: 2; Grade 9: 3; Grade 10: 1 |  |  | 10 | Completed in June 2005 | Items 1,2,3A
24 | MGR Nagar Kasimedu Chennai 81 |  |  | Grade 6: 1; Grade 8: 6; Grade 9: 2; Grade 11: 1 |  |  | 10 | Completed in June 2005 | Items 1,2,3A
25 | Mullaikuppam Chennai-28 |  |  | 2 | 1 | 9 | 3 | 2 | 2 | 9 | 3 | 4 | 4 | 1 |  |  |  | 40 | Completed in June 2005 | Items 1,2,3A
26 | Mattankuppam chennai-5 |  | 1 |  | 1 | 3 | 3 | 7 | 1 | 5 | 5 | 1 |  | 1 |  |  |  | 28 | Completed in June 2005 | Items 1,2,3A
27 | Netaji Nagar Beach Road Ennore |  |  | 1 |  |  | 1 |  |  | 1 | 2 | 1 | 1 | 2 | 1 |  |  | 10 | Completed in June 2005 | Items 1,2,3A
28 | Andikuppam Village Pazhaverkadu |  |  | Grade 3: 1; Grade 5: 3; Grade 6: 1; Grade 7: 1; Grade 8: 2; Grade 9: 1; Grade 10: 1 |  |  | 10 | Completed in Aug 2005 | Items 1,2,3A
29 | Kottai kuppam Pazhaverkadu |  |  | Grade 5: 1; Grade 8: 1; Grade 10: 3; Grade 11: 3; Grade 12: 1 | 1 |  | 10 | Completed in early July 2005 | Items 1,2,3A
30 | Naduvur Mada Kuppam Pazhaverkadu |  |  |  |  | 3 | 1 |  | 2 |  | 2 | 3 | 8 | 15 | 22 |  |  | 56 | Completed in sept 2005 | Items 1,2,3A
31 | West Kottaikuppam Pazhaverkadu |  |  | Grade 6: 2; Grade 7: 2; Grade 8: 1; Grade 9: 1; Grade 10: 2; Grade 11: 5 |  |  | 13 | Completed in sept 2005 | Items 1,2,3A
32 | Nochikuppam Chennai-4 |  |  | Grade 1: 1; Grade 3: 2; Grade 4: 1; Grade 6: 2; Grade 7: 4 |  |  | 10 | Completed in Oct 2005 | Items 1,2,3A
33 | Nadukuppam Chennai-5 |  | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 |  | 1 |  |  | 1 |  |  | 12 | Completed in sept 2005 | Items 1,2,3A
34 | Thondaiyarpettai near Kasimedu | 1 | 1 | Grade 4: 1; Grade 6: 3; Grade 8: 3; Grade 9: 1; Grade 10: 1; Grade 11: 3 |  |  | 14 | Completed in Oct 2005 | Items 1,3A
35 | GM Pettai Kasimedu |  |  |  |  | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 1 |  |  |  | 14 | Completed in Oct 2005 | Items 1,3A
36 | YMCA Kuppam Kasimedu |  |  | 1 | 3 | 1 |  | 1 | 1 | 1 | 1 | 1 | [5 empty] | 10 | Completed in Oct 2005 | Items 1,3A
37 | Srinivasapuram |  |  |  | 10 | 3 | 10 | 12 | 7 | 8 | 9 | 12 | 9 | 5 |  |  |  | 85 | Completed in Oct 2005 | Items 1,3A
[17 empty] | Total number of students helped back to school | 2095
[17 empty] | Total funds raised for the project from various sources |  | 1416350
[17 empty] | Total expenses January 2005 to October 2005 |  | -1416209
[17 empty] | Balance |  | 141