# MEMORANDUM OF UNDERSTANDING

Asha for Education and Doorstep Schools (Pune)

2004-2005

Agreement between “partners”:

# Asha-Atlanta

Contact person: Ashok Narayan

Address: ashoknarayan_ashaATyahoo.com

# Asha-Seattle

Contact person: Vidyanand Rajpathak

Address: vidrajATmicrosoft.com

# Asha-Pune

Contact person: Sujata Mulye

Address: sujatamATvxindia.veritas.com

And

Doorstep Schools (Pune)

Contact person: Mrs. Rajani Paranjpe

Address: 110, Anand Park, Aundh, Pune 411007.  Phone: 91-20-25898762, Fax: 91-20-25893866, dsspune(AT)vsnl.net, k_paranjpe(AT)vsnl.com

The following has been agreed upon:

- Tasks planned to be undertaken by Doorstep Schools:

- To conduct study classes for children attending government school and non-formal education classes for out-of-school children in the age group of 7-14 years living in the Laman Tanda area

- To set-up and maintain a reference library and study center in the Laman Tanda area

- Commitments of Doorstep Schools working in the Laman Tanda area:

- To run two study classes for children (age group 7-14 years)

- To run two non-formal education classes for out-of-school children (age group 7-14 years)

- To set up a reference library and study center, and a children’s library

- To employ teachers for the classes, and a library worker for the library

- To procure educational materials for the children in the classes, books and furniture for the library

- To educate the children to improve their literacy

- To create a nurturing and fun learning environment for the children so as to increase their retention in the formal or non-formal schooling system

- To take the children out for picnics/trips at least 6 times during the funding period

- To gradually sensitize the local community about the importance and relevance of education

- To maintain detailed records of the academic progress of every student

- Expected outcomes after a year of training

- Basic literacy for students attending NFE schools

- Students attending study classes should pass school examinations

(All – is part 3 ok or do you feel that we can define this somewhat better?  This should give DSS a clear idea of what kind of outcomes we expect)

- Financial plan:

- Appendix 1 is the agreed expenditure break up for the project during 2004-05.

- Commitments of Asha-Atlanta and Asha-Seattle

- Asha-Atlanta has agreed to fund the project to a level of Rs.x for the school year 2004-2005 in two installments. Continued funding for future years will be contingent on the performance in the first year.

- Asha-Atlanta shall release funds for the second installment at the end of six-months. This will be against submission of satisfactory reports on both the education component and the expenditure during the first 6 months by Doorstep Schools.

- Asha-Seattle will fund the remainder for the school year 2004-2005 (Rs.2,30,000 - x) in two installments.

- Asha-Seattle shall release funds for the second installment at the end of six-months. This will be against submission of satisfactory reports on both the education component and the expenditure during the first 6 months by Doorstep Schools.

(All – please take a look at the budget in Appendix 1.  I have questions about the highlighted items.  Once, we fix that, we can put numbers into this.  Sujata Mulye – the Asha Pune project owner is unavailable till the 15th, so I am not sure whether these questions have already been addressed.  Also, would both Seattle and Atlanta want to fund in two parts, or would you prefer to fund first six months/next six months?)

- Commitments of Asha-Pune

- Asha-Pune shall assist Asha-Atlanta and Asha-Seattle with periodic project visits and reviews.

- Asha-Pune shall also actively liaise between Asha-Atlanta and Asha-Seattle and; Doorstep Schools.

- Timelines, milestones and related administrative commitments

- Start of project: On receipt of funds by Doorstep Schools.

- 6 months: Submission of 6-month reports by Doorstep Schools

  - Report 1: Education component (including progress records of students and status of library, procurements and usage)

  - Report 2: Expenditure statement (against financial plan heads)

- 6 months: Site visits by Asha-Pune and submission of visit report to Asha-Atlanta and Asha-Seattle.

- 6 months: Review of Doorstep Schools reports and visit reports from Asha-Pune by Asha-Atlanta and Asha-Seattle followed by release of second installment.

- 12 months: Submission of final reports by Doorstep Schools

  - Report 1: Education component (including progress records of students and status/usage of library)

  - Report 2: Expenditure statement (against financial plan heads)

- 12 months: Submission of proposal for school year 2005-2006 by Doorstep Schools

- 12 months: Site visits by Asha-Pune and submission of visit report to Asha-Atlanta/Asha-Seattle.

- 12 months: decision on continued funding by Asha-Atlanta/Asha-Seattle.

- Project visits

- Doorstep Schools agrees to allow members of Asha to visit the project sites.

- Other

- This MOU will be suspended if either of the parties fail to honor any of their above mentioned commitments.

Agreed:

Date:

(For Asha-Atlanta) (For Asha-Seattle)(For Asha-Pune)(For Doorstep Schools)

Appendix 1:  Budget required by Doorstep Schools for 2004-05

| Heads | Per Month | No | No. Months | Total |
| --- | --- | --- | --- | --- |
| I. PROGRAMME STAFF SALARIES |
| Co-ordinator (Part salary) | 4000 | 1 | 4000 x 13 | 52,000 |
| Study and NFE class teachers (4 hours daily) | 750 | 4 | 750 x 4 x 13 | 39,000 |
| Community & Reference Library worker | 1500 | 1 | 1500 x 1x13 | 19,500 |
| Child-care centre worker | 1400 | 1 | 1400 x 1x10 | 14,000 |
| Recreation centre worker ( 2 hours daily) | 300 | 2 | 300x2x13 | 7800 |
| Vocational centre worker ( part time ) | 750 | 1 | 750x1x13 | 9750 |
| Total of I |  | 10 |  | 142050 |
| II- PROGRAMME EXPENSES |  |  |  |  |
| Teaching &educational material per child for 150 children | 10 | 150 | 10 x150 x12 | 18,000 |
| Picnics, camps etc for the children approximately 6 in the year | @Rs. 10 per child | 150 | 10 x150 x6 | 9,000 |
| Total of II |  |  |  | 27,000.00 |
| III Other expenditure |  |  |  |  |
| Rent for 3 rooms | 300 |  | 12 | 3,600 |
| Purchase and maintenance of books (Adults, Children & Ref. Library) | 15000 | one time |  | 15,000 |
| Purchase of furniture etc. | 15,000 | ,, |  | 15,000 |
| Total of III |  |  |  | 30,650 |
| Total of I +II+III = 199, 650 |  |
| IV Administrative expenditure ( telephone, stationary, postage, travelling and such other expenditure) @ 15% of I+II+III |  |  |  | 30,000 |
| Total of I+II+III+IV |  |  |  | 229,650. 00 |

- No. of children covered will be 250 (40-50 children in each study class, non-formal education class = 200, other 50 for library)

- 4 different types of services provided (study classes, NFE classes, library and study center cum reference library)

- Per child cost per year is Rs. 1000. 00 approximately.