wwProject Name – Mahila Swarojgar Samiti ( MSS)

Location – Raja Talab, Varanasi, UP

Project sponsors- U Penn, Ajay Jethi

I visited Varanasi as part of the Asha 6 monthly conference, held on May 25-26. I conducted an on-site visit and  evaluation of the MSS

project. Please find attached relevant project details.

1. Summary

I find the current state of the project satisfactory.  We are currently in very early stages of the project and there is potential to improve

some of the existing practices. There is optimism among the project organizers and the ASHA team that this project will be able to

achieve it’s objectives in the next 3 years

Solid foundations for the project are being laid down. Key highlights include:

-          Excellent local community involvement

-          Resilience, spirit and networking of the project organizers

-          Existence of self help groups in 20 villages in the area, which would be leveraged to promote income generation activities

An incremental funding of Rs 8,000 for the FY 2002 is requested for. This would entail the purchase of 1 sewing machine for Todapur

( Rs 3,000 ) and purchase of books which would allow all the 250 students to gain access to books teaching Govt curriculum ( Rs 5,000 )

Another proposal, would be circulated by the project team in the next few weeks. This would be to recommend approval of incremental

funds in 2002 and beyond, to manage a day center for the physically and mentally challenged children.

2. Background

## General Information

Raja Talab is located approximately 25 kms from Benares town. The 4 centers being supported by Asha all lie within a radius of 10

kms in this area. The centers operate in villages where Scheduled Castes and backward castes are in a  majority.

The limited government schemes in operation for the upliftment of these communities have not had much  impact.  Massive

corruption and lack of awareness among the people of their rights could be cited as major factors  for  the poor track record of these

schemes

About 6,000 people live in these 4 villages, where Asha centers are running. Most of them live below the poverty line.  Backward

caste people, do not own any land.

Sari weaving is the economic mainstay for most people in the area. Even in this activity, the villagers are dependent on  and are

exploited by the middlemen in the trade, which translates into very little margins for the craftsmen in the villages.

MSS Organizers

In the year 2000 and 2001, Ms Rekha Chauhan, started self help groups in 20 villages and child literacy classes in 10  villages in the

Raja Talab area. She was inspired by Mr. Iqbal Singh, who believes in the Gandhian ideology. She has great potential and has a good

reputation in the community. However, today child classes exist in only 2 of the centers due to paucity of funds

Rekha has been supported till now by a Rs 1500 per month honorarium by a foundation in Renukoot ( UP)  ( will finish at the end of 2002 and will not be renewed due to foundation rules). She apparently does not receive any other funding

Asha India conducted a site visit in November 2001 and very strongly recommended ASHA supporting this project.

U Penn along with Ajay Jethi have been involved in this project since Q1, 2002

3.  Strategic Goals and implementation plan

| Project Objectives | Project Strategy | Action Plan |
| --- | --- | --- |
| 1. Provide quality basic education to at least 90 % of children in the 4 adopted villages by the year 2004 | 1. Aggressively target children from marginalized communities ( Mushair, Ahir etc) | Locate schools closer to residence of deprived communities (Ex – Todapur) |
|  |  | Increase community involvement by initiating monthly PTA meetings ( starting July 2002 ) to provide feedback to parents and elicit suggestions |
|  |  | *Raise minimal fees from children with relatively well off backgrounds (ex Yadav), so that deprived community children can have better access to schools |
|  | 2. Utilize non-formal teaching methods ( songs, plays, etc.) to generate and sustain child interest in school attendance | Leverage Nandlal’s “ Nautanki” troupe expertise and train 4 child center teachers from July 2002 |
| 2. Ensure self reliance and substantiality of project by Year 3 of funding ( 2004) | 3. Develop vocation based training skills to impart self sufficiency among village women and the project | Raise proposal to purchase sewing machine for sewing and embroidery classes in Center 1 in 2002. Similar proposal for other 3 villages by 2003 |
|  |  | Utilize existing Mahila Samithi to build awareness support for training programs |
|  | 4. Leverage the popularity of “Mahila Samithi” groups to devise and find income generation projects | Test market and evaluate reaction to Agarbati and Silk thread scheme in 2002 |
|  |  | Investigate market potential for launching other income generation concepts ( Dal, Nursery, Gulbashan) from 2003 onwards |

*    Admission fee of Rs and a monthly tution fee of Rs 2 will be obtained from selective children ( predominantly Yadavs who sell milk and can afford it. The money would be used for operational maintenance

4. Current Project Status ( prior to ASHA funding)

- Current MSS team of Rekha and 3 teachers

- 2 children educational centers and 1 women center ( without vocational training ) currently running

- Local community involvement is forthcoming. Villagers themselves have come forth with requests for schools to be built

- Gram panchayat has allocated land for the Harfos Centre

Attached is a brief summary of the 3 centers currently in operation :

|  | Todapur | Harfos | Harpur |
| --- | --- | --- | --- |
|  | Child Centre 1 | Child Center 2 | Woman Centre 1 |
| Communities resident | Mushair, Ahir, Yadav | Mushair, Chamar, Rajbahar | Chamar |
| Number of students | 80 | 100 | 10 girls |
| Age-group of students ( years ) | 3-15 | 3-15 | 10-18 |
| Gender Ratio ( Male : Female) | 50 : 50 | 50:50 | 100 % Female |
| Number of teachers | 1 | 2 | 1 |
| Number of women in women center | N-A | N-A | 20-25 |
| Frequencies of classes /meetings | 6 days a week | 6 days a week | Once every month |
| Course content * | No textbooks used Oral briefing for Hindi, English, Math and history subjects | No textbooks used Oral briefing for Hindi, English, Math and history subjects | Educate women about education issues, hygiene, cleanliness Girls are given oral briefing similar to the other 2 centers |

* Currently 5 classes are held every day in all the 3 centers.  The children are segregated based on their age groups and attend

one of the classes. Classes cover Class 1 – 5. Objective is to try and impart leaning, which would allow the children to join

either the Govt School or the Open school after Class 5

5. Project Financials ( Current – APPROVED)

Funding approved for Year 1 is Rs 48,400. Details are attached below :

| Activity | Expense and Duration | Total expense |
| --- | --- | --- |
| Salary for teachers at the 4 centers | 4 X Rs 200 X 12 | Rs 9,600 |
| Salary for 3 teachers at Todapur branch | 3 X Rs 700 X 12 | Rs 25,200 |
| Educational material for 4 centers * | 4 X Rs 400 | Rs 1,600 |
| Blackboard for the main branch | 3 X 400 | Rs 1,200 |
| Stationary for main branch | Rs 400 X 12 months | Rs 4, 800 |
| Travel expenses | Rs 300 X 12 months | Rs 3, 600 |
| Office Expenses | Rs 200 X 12 months | Rs 2, 400 |
| TOTAL |  | Rs 48,400 |

* Covers only blackboard + chalk

6. Additional activities with Year 2002 approved funding

Asha approved budget of Rs 48,400 will be implemented from July 2002 * onwards. List of incremental activities which will be implemented are attached below :

|  | Todapur | Harfos | Harpur | Chahranpur |
| --- | --- | --- | --- | --- |
|  | Child Centre 1 | Child Center 2 | Woman Center 1 | Woman Center 2 |
| Number of students | + 70 | + 25 | Same | 10-15 |
| Number of teachers | + 2 | Same | Same | + 1 |
| Number of women in women center | N-A | N-A | Same | 20 |
| Frequencies of classes /meetings | Same as earlier | Same as earlier | Once every month | Once every month |

* Schools generally close during the summer, as the children are not available during the period of April - June

Incremental funding of Rs 3000 , is requested for purchasing a Sewing machine for the Todapur Centre. This would impart vocational skills to the women in this village. This ties in very well with sari weaving which is the economic mainstay of the area.

In addition, Rs 5,000 would be utilized for buying books.  Currently the teachers are giving oral briefing to the students in the absence of books. The books would have a government school syllabus. The cost would cover the expense of books for all the 250 students in the 4 centers ( Rs 20 per student X 250 students = Rs 5,000 )

7. Key Project Challenges

       Sustainability of organizational structure :  – Rekha Chauhan needs to build a team, which can drive and sustain the ambitious activities planned in the next few years. Currently, Rekha is running the show almost single-handedly. During my discussions with her, we agreed that she needs to focus more on identifying women with potential and then groom them for leadership roles.

       Developing skills for marketing products/ services initiated under income generation schemes : - Proposed schemes to make the project self –reliant will require specific skills in packaging, communicating the product / service etc.. Currently, as Rekha herself admits, lack of training and experience in this area is a big constraint and impacts the off take on these products from the retail outlets.

This results in the retailers, insisting on credit from MSS, while purchasing the product. The cash flow of the project is impacted and it has a spiraling effect, as Raw material cannot be purchased.

We also need to link this with the proposed “ Asha –shop” concept, where all Asha supported products would be sold under 1 roof ( proposed at Kaithi conf) .

     Ensuring drop out rates are low and children attend school : - As demonstrated in other projects, making the process of leaning more playful and enjoyable is one of the key factors in keeping children interested in school. In addition, some Givt schemes like the Anganwadi  ( near Centre 1), tempt parents and children alike with the promise of a free mid-day meals.

MSS is keenly aware of this and is putting into practice concepts like songs and “nautankis” to catch the children’s attention. However considering the economic condition of most villagers, ensuring children regularly attend school, will be a constant challenge

   Linking content taught in our schools to a more mainstream curriculum :- As mentioned previously, currently students are being taught by giving them only a oral briefing. With books, being procured, the teaching methodology would hopefully become more interesting and linked to the mainstream curriculum.

- Leveraging education skills and local community relationships to manage the proposed school for physically / mentally challenged children : - A proposal has come through from the Gram Panchayat of a nearby village to manage a center for the “challenged” . The panchayat would donate the land as well as build the house in which the center will be located. There is no such center to deal with the challenged in the nearby villages.

Rekha Chauhan is quite confident that she would be able to manage this with her  team. More details on this proposal would be available in the next few weeks. It needs to be carefully debated and discussed among the Asha team.

8. Key project milestones

| Activity |  | 2002 |  |  |  | 2003 |  |  |  | 2004 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Test Market of Agarbati |  |  |  |  |  |  |  |  |  |  |  |  |
| And Silk thread concept |  |  |  |  |  |  |  |  |  |  |  |  |
| commences |  |  |  |  |  |  |  |  |  |  |  |  |
| Women Centre at Chahranpur |  |  |  |  |  |  |  |  |  |  |  |  |
| village opens |  |  |  |  |  |  |  |  |  |  |  |  |
| Sewing machine training |  |  |  |  |  |  |  |  |  |  |  |  |
| at Todapur starts |  |  |  |  |  |  |  |  |  |  |  |  |
| Training of teachers by |  |  |  |  |  |  |  |  |  |  |  |  |
| Nandlal's" nautanki" |  |  |  |  |  |  |  |  |  |  |  |  |
| "Challenged" center |  |  |  |  |  |  |  |  |  |  |  |  |
| ( if approved) to commence |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | 2002 |  |  |  |  |  |  |  |  |  |  |
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Test market of Dal and |  |  |  |  |  |  |  |  |  |  |  |  |
| Nursery concept |  |  |  |  |  |  |  |  |  |  |  |  |
| 2nd sewing machine |  |  |  |  |  |  |  |  |  |  |  |  |
| Purchased for Harfos |  |  |  |  |  |  |  |  |  |  |  |  |
| Implement Dal and Nursery |  |  |  |  |  |  |  |  |  |  |  |  |
| Concept in Todapur |  |  |  |  |  |  |  |  |  |  |  |  |
| 3rd sewing machine |  |  |  |  |  |  |  |  |  |  |  |  |
| purchased for Harpur |  |  |  |  |  |  |  |  |  |  |  |  |
| Implement Dal and …. |  |  |  |  |  |  |  |  |  |  |  |  |
| Concept in Harfos |  |  |  |  |  |  |  |  |  |  |  |  |
| Self-Sufficiency of project |  |  |  |  |  |  |  |  |  |  |  |  |

9. Next Steps

| Task | By Whom | By When |
| --- | --- | --- |
| Cheque to cover remaining approved budget for 2002 to be received by MSS | U Penn | 2nd wk June ‘02 |
| Request for sewing machine to be evaluated by Asha project team | U Penn, Ajay, SKI, Asha- Kaithi | 4th Wk June ‘02 |
| Proposal on challenged center to be presented Evaluation by Asha project team | Rekha, Ajay U Penn, Ajay, SKI, Asha- Kaithi | 4th week June ‘02 3rd wk July ‘02 |
| Gather details on funding by Govt to gram panchayats in the 4 villages | Rekha | July ‘02 |
| Prepare a project progress report every quarter | Rekha | July ’02 ( 1st report) |
| Gather details on proposal for introducing project performance metrics ( circulated in recent Asha-wide e-mail) | Ajay | July ‘02 |
| Hold conference call every 6 months to review project progress | Ajay, U Penn, SKI, Rekha | Aug ’02 ( 1st call) |
| MSS to submit funding requirements for Year 2003 | Rekha | Nov ‘02 |
| Income Generation Activities |  |  |
| Monitor progress of Agarabati and silk thread activities | Rekha | Till Oct ‘02 |
| Evaluate and analyze key learning’s from Agarbati and silk thread endeavors | Rekha, Ajay | Nov ‘02 |
| Present proposal to introduce Dal + Nursery activities | Rekha, Ajay | Dec ‘02 |