## SAHANIVASA

## A project to “Promote the livelihood Rights of Marginalized Communities through NREGA (National Rural Employment Guarantee Act)”

#### Duration: Three years from the date of sanction, however only first year project                 Budget is projected in the project.

Geographical Area:

This project is aimed to cover 10 mandals but for all practical reasons the project budget is planned for one mandal. Therefore, the budget can be multiplied according to the number of mandals covered if there is possibility for raising support.

- K.V.Palli – The project is budgeted for this Mandal.

- G.D. Nellore

- Piler

- Sadum

- Palasamudram

- Chittoor

- Pulicherla

- Kalakada

- Gudipala and

- Kalikiri

Objectives of the project:

- Stop the Child labour and dropouts in the school utilizing NREGA for 100 days by the rural poor landless workers.

- To enhance livelihood security of landless unemployed rural workers and their family members.

- To convert uncultivable lands of rural poor into cultivable productive assets of the rural poor through the better implementation of employment guarantee schemes.

- Enhance the capacities of the rural workers to make use of right to information act and EGA to work towards transparent and corruption free societies.

- Develop leadership skills among the youth to involve in better implementation of NREGA.

- To build the collective skills of protest and dissent from among the agricultural workers and Dalits of local area against the corruption non-implementation programs.

Strategies:

- Take up NREGA campaign to stop child labor.

- Strengthen the Agricultural Workers Unions for better implementation of NREGA

- Work very closely with panchayats and Government Officials.

Back Ground Of The Project:

Andhra Pradesh Vyavasaya Vruthidarula Union-APVVU is one of the few organizations long time demand for employment guarantee act is actualized as The National Rural Employment Guarantee Act -2005 (NREGA).  Ever since Andhra Pradesh Vyavasaya Vruthidarula Union-APVVU has started releasing the bonded labour and demand for minimum wages in late 80’s, the wider level demand has been the EGA. Some of the milestones of two decades journey of the campaign for EGA are;

- Submitted ten million signatures to Dr. Kumud Bhen Joshi, the then Governor of A.P., in 1989.

- District wide and statewide rallies, consultations and protest programs for half decade.

- Submitted series of memorandums in the Public Hearings organized by Second Labour Commission in 2003, demanding Employment Guarantee Act.

- Organized State level consultations and National level collective mass campaigns all

through the years by lobby with the MLA’s and MP’s

- Negotiated with Congress the then opposition parties and communists to include the EGA in their election manifesto in 2005.

- Advocacy and lobby with legislatures and parliamentarians to include EGA Common Minimum Programme of the present UPA Government

- Conducted series of programs and demonstrations in front of State Assemblies and

Parliament while the sessions was going on.

Role of SAHANIVASA in NREGA:

SAHANIVASA has been of the organizations very strongly supported and promoted APVVU process in Andhra Pradesh when it is realized that NGO’s has limitations to take up genuine rural poor problems in Rights based approach.  In mid 80’s Sahanivasa has emerged as an go to release the bonded labour and rehabilitate them.  Though the release of bonded labour is sanctioned by the law. It is very difficult to handle has an NGO since the same powerful landed lobby were in power to violate the law.  So in order to take up as people’s response to the bonded labour situation we have to promote civil societies organisations not only in chittoor region where SAHANIVASA works and also all over Andhra Pradesh.  The civil society organisations were consciously promoted and converted as registered Agricultural Workers Unions.  SAHANIVASA has played key role in strengthening the State level federation of Agricultural workers as APVVU. By deputing Mr. P. Chennaiah, the founder Secretary of SAHANIVASA to work full time for the APVVU process through out the state.

# The context of NREGA

The UPA Government has come out with the Act in the context of agricultural economy is in   big Crisis where the agriculture is not in position to absorb any employment beyond 70 days in a year. The cumulative impact of 9 years drought led to migration of vast majority rural workers.  Migration from rural area means displacement from their homelands, traditions and cultures, which are equally important for rural people to survive as a community. The community living has been in disturbance due to wide spread unrest, hunger deaths of old people, frustrations, hungry situations prevailing in Rural workers families. It is in this situation, EGA is perceived as a tool to be applied to protect the rural mass from the hunger and displacement. Despite of its limitations – hundred days employment in a year and applicable only for 200 districts – this act has to be properly implemented to achieve the objective of providing the employments for the most needy.

The government of India has allocated Rs. 160,000 millions during this year budget to meet the employment requirements of workers of 100 days in 200 districts. The other important aspect of this act is that the employment for rural workers has to be provided by the government at the walk able distance of their habitation. By any reason if the  Government is failed to provide the employment, the workers  are eligible for the  compensation of  25% to 45% of minimum wages per day  Further they are allowed to work to improve the rural infrastructures that include developing the uncultivated lands of the poor families.  The minimum wage is fixed as Rs. 80 in Andhra Pradesh (Rs. 60- Central Government share & Rs. 20 – State Government Share), which is almost three times more than what they are getting today in agriculture.

Why SAHANIVASA to work for this:

The EGA program is designed in such a way that every registered worker and their group should be provided work within the fifteen days of request.  Further the workers should be paid the wages on weekly basis where lot of money in flow and transaction take place.  Though the government has taken all necessary steps to reach the amount to the actual beneficiary, the state cannot be free from highly experienced corrupt bureaucrats and the political Maphia loot the resources to diffuse the Act,.  Therefore the need of the hour is to ensure that every single rupee allocated by the government to reach the genuine to rural worker.  This will be possible only by way of ensuring the people’s participation with all the knowledge and systems, rules and regulations about the NREGA. So that people will be able to collectively demand their due share without bending for bribe. The unions only can provide confidence in the capacity of people’s power to withstand the threats of Western interest groups.

.

Present Status:

The implementation of NREGA has completed 26 motnhs of its implementation. As it has been expected wherever people are involved as collective in the process of all the stages until they get the wage there is less chances of corruption. In other words, wherever people are not organized and sensitized, the middle men have been filling their pockets everyday denying the wages.

So for role of SAHANIVASA & APVVU has already involved and influencing the government and also participate in the planning process. Therefore the need of the hour is to participate at gross root level to sensitized and organize the masses and also coordinate with the state authorities to maintain transparency and accountability of the implementation, then only the fruits of the Act will reach the needy.

So for the role of APVVU has been:

- 8.45 lakh workers got the job cards in 14 districts.

- District secretaries of APVVU have undergone Trainers training program engaged by the government.

- The Trained leaders are listed as State Monitoring committee of EGA

- The Unions have been identifying the works and put up the application for employment and many works has been in force.

- while the state has accomplished only 32 days of employment in the year, SAHANIVASA is able to make it 56 days in the last year – the target should be 100 days.

- 20% of migration is stopped in the area which needs to improve as 100% workers should stop migration.

Gaps in NREGA identified in Social Audit as follows:

- Lack of awareness about the scheme among the general public.

- Laborers are not given the opportunity to take decision regarding the selection of works.

- Officials not accepting the applications for work.

- From the time the work is started, the measurements taken and the wage payments every week is not informed to the laborers.

- Delay in the wage payments.

- Laborers are not getting minimum wages.

- Prior to starting the work, the laborers are not given details regarding the work estimation, cost of work and rate of the work.

- During the wage payments the pay slips are not given to laborers.

- Once the work is over in one place, the next work is not shown immediately.

- The facilities mentioned according to law are not properly provided at the work place.

- The tools necessary for the work are not provided.

- The officials are not responding to the injuries occurring during work in the work spot and the compensation is not paid.

- The officials are not telling the work properly to the laborers.

- The middle men and the contractors interfere in the implementation of this scheme.

- Laborers who don’t have post office accounts are not given work.

- Lack of awareness about the scheme to the field assistants and the technical assistants.

- The political cadre appointed as the field assistants has spoiled the real implementation of the program.

- People are not accepting these works as their rights.

- The NGOs and the People’s organizations are not made a part of the implementation of this program.

- People working in binamy names and getting paid.

Proposed Activities:

To actualize the objectives and strategies into practice we plan the following immediate activities

- Education and building people’s advocacy

- Training Youth Volunteers

- Cultural Training and Performances for Propagation

- Building linkages among the People and the government Officials

- Strengthen the Village Level Workers Associations

- Identify the appropriate works for Employment

- Activate Gram Panchayat

- Public Hearings at Mandal Level

- Social Audit

- Week long Caravan for Propagation, Implementation and Monitoring

- Education and building people’s advocacy:

NREGA program is planned   to provide 100 days employment for the   most marginalized groups in rural areas. These are the people do not have much literacy background and their resources can be easily manipulated by the officials. This is the program can be successful if the needy are full aware of the provisions and also the procedures of the Act. Further their participation at all levels will ensure the   end of corruption.  Therefore the real needy people are to be united as pressure group to implement   the program.  The main core of the activities are:

- Bring out the brief pamphlets on the rules, regulations & procedure to be followed in NREGA scheme

- Conduct village wise caravan /campaign in mandal once in every 6 months to build confidence and   to raise their voice against the bureaucrats non Co-operation, corruption and any discrepancies of implementing EGA

2. Youth Volunteers Training on NREGA:

Conduct youth volunteer training program for 4 days selecting from different villages in the mandal so that they could able to help the workers’ collectives to get the employment opportunities. The youth will be trained on registering the applications for jobs, getting works for the workers, petitioning for bills payment, conducting social audit, educating the villagers, monitoring the proper implementation of NREGA, distribution of education materials etc.

3. Cultural Training and Performances for Propagation:

Majority Labourers for whom the NREGA is introduce or illiterates.  While the pamphlets and other education material address the literates and youth the education through the cultural action will reach the majority labourers.  Rural labour will be informed about the various positive provisions of the act, rules and methods of implementing the NREGA through the songs and skits, so that   they will be able to understand it well.  Youth from the rural area will undergo seven days cultural training, so that they can perform the programmes in  villages  at night times.

4. Building linkages among the People and the government Officials:

EGA is considered as extra work to officials.  Hence they do not find time to pursue the matters on EGA.  As results the middlemen replace the role of Mandal Development Officer (MDO) and the concern officials. Hence the need is to build the linkages among the people and the government officials for proper implementation of the Act. To achieve this, we propose the following activities.

- Plan for coordinated activity through out the district where People will be reached by way of padha yatra from different corners of the district.

- Visit the work spots by padha yatris to collect the data on status of each of the work.

- Take up capacity building programme for yatris before they go for padha yatra on the Act and also its favorable spaces. so that they will communicate better with the people in villages.

- Final concluding meeting can be organized where the consolidated report can be submitted to the officials to follow up.

- Media and concern citizens will be encouraged to be part of the process.

5. Strengthen the Village Level Workers Associations:

The Act provides opportunity for all the registered workers in each village can be formed into groups to apply for specific works.  In others words this act provided space for collective work.  It is also important to note that the collective work and collective bargaining is always benefit to the people in the manner of getting more work, demanding the wages on time maintain the transparency etc., Hence, there is a great need to strengthen the village level workers associations who in turn will play creative role in successful implementation of the Act.  The  the emphasis is to see that the workers meet regularly in the village to plan for the work, file the application, follow up with the officials for sanction, implementation, verification and measurement of the work by official, payment of wages and maintains the records in transparent manner.

The Mandal Organiser  will follow up all the activities in the mandal as :

- Develop women workers association is another important activity.  Though men and women work collectively in the same work demand the equal wages is an important issue.

- Secondly, women & disabled specific needs at work spots can only be put forward strongly by women when they are in collective.

- Sexual abuse at work place is an issue everywhere, which will also be, take up by the women task force.

- Develop separate association for women workers is benefit to the workers

Therefore, one of the main focuses of this project is to see that women workers should have their own identity in every village,.

6. Identify the appropriate works for Employment:

The Act emphasizes to provide hundred days employment for the workers   in un-season. The government has listed out 71 types of works under the EGA.  Some of the listed are also to develop the infrastructure facilities of the lands of small and marginal farmers of Dalits and Adivasi communities.  But the government officials will not give priority to select the works which help the poor people to develop their infrastructure facilities.

For example, in a village where there is a possibility for selecting the works for reclamation of degraded lands, construction of field tanks, field bundings the government officials give priority of de-silt of tanks  and laying the roads,  This way they avoid the development of the infrastructure facilities of the vulnerable communities.  Keeping this trends in view we have plan  to involve at every village level to identify the appropriate works.  So that the labourers get dual benefits of employment and also strengthen the livelihood resources.

7. Activate Gram Panchayat:

Gram Panchayats has an important role in NREGA.  This is the primary unit of the administration responsible for the implementation of NREGA.  As per the Act, Gram Sabha should play key role in identifying and approving the specific works, open the single Bank account to transfer the grants, Payment of the wages, and maintain the accounts.  This is the programme where Gram Panchayat cannot get any remuneration for the administration.  Therefore they will not be showing interest to take up the work if the workers in the village are well aware of the provisions of the act.  On the other hand the panchayats will loot the NREGA funds if the people are not active.  Therefore while sensitizing the people for better utilization of the scheme we do have to activate panchayats simultaneously,  So that the Panchayat leaders will not swallow the funds of NREGA.

8. Public Hearings at Mandal Level:

Yearly Once we have plan to conduct public hearings at mandal level on the implementation of NREGA.  So that the people involved in implementation will be careful to get out of the public exposes.  The reports will be submitted to the government in order to rectify the discrepancies.

9. Social Audit:

The act provides space for transparency and accountability of the funds allotted for NREGA.  Further every work can be made available for public scrutiny and social audit.  The basic objective of the Social Audit is to ensure the public accountability in the implementation of the

NREGA.  The innovative aspect of the NREGA is incorporating Social Audit as part of the Act. Our fear in this is that this also becomes a paper tiger if people are not vigilant in conducting Social Audit,  Which should be a continuous process right from the registration of families, distribution of job cards, receipt of work applications, selection of the work, development and approval of technical estimates, sanction of the work order, allotment of work to individual and youth, supervision of works, payment of unemployment allowances, payment of wages and evaluation of work.

At every stage there is scope for corruption.  Therefore social audit is mandatory which can be implemented only against the demand.  Unless this is conducted it is difficult to stop the corruption.  Therefore we have plan to conduct the social audit.  APVVU district secretaries are selected as State Vigilance committee members who are empowered to conduct the Social Audit in cooperation with the government officials.

10. Week long Caravan for Propagation, Implementation and Monitoring:

To carry on all the above mentioned activities there is great need to conduct a caravan for a week days to ten days, all over the area through which we reach the unreachable communities to propagate about the Act, and take up all the listed activities that are mentioned above.  The caravan can be concluded with public hearing at every mandal in which the officials can also be part of it.

Personal Required:

We propose one organizer for each mandal. Role of this person is to take up all the above tasks that are mentioned in the Social Audit, in addition to organize, educate, Identify the works , advocate for approve the works and  implement NREGA projects.  This organizer will be the key player for all these programs.  Generally, we select the person from the same mandal so that the person knows everything about the mandal.

WORK PLAN & TIME TABLE

| Program Particulars – Month Wise | Month Wise Plan |
| --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Program |  |  |  |  |  |  |  |  |  |  |  |  |
| Education and People’s Advocacy |  |  |  |  |  |  |  |  |  |  |  |  |
| Village level Education campaign and meetings | * | * | * | * | * | * | * | * | * | * | * | * |
| Cultural Training | * |  |  |  |  |  |  |  |  |  |  |  |
| Pamphlets and education materials |  | * |  |  |  |  |  |  |  |  |  |  |
| Youth volunteer Training on NREGA |  | * |  |  |  |  |  |  |  |  |  |  |
| Organization and Mobilization |  |  |  |  |  |  |  |  |  |  |  |  |
| Strengthening Village level labour Associations | * | * | * | * | * | * | * | * | * | * | * | * |
| Women form separate Association | * | * | * | * | * | * | * | * | * | * | * | * |
| Identify the works and applications |  |  | * | * |  |  | * | * |  |  |  |  |
| Formation of Committees for various tasks |  | * | * |  |  |  |  |  |  |  |  |  |
| Panchayat approvals and Gram Sabha meetings |  |  |  | * |  |  | * |  |  |  | * |  |
| Week long Caravans / Padha Yatras at Mandal Level |  |  | * |  | * |  | * |  |  |  |  |  |
| Evaluation, Monitoring and Transparency |  |  |  |  |  |  |  |  |  |  |  |  |
| Public Hearings |  |  |  |  |  |  |  |  |  |  | * |  |
| Social Audit |  | * |  | * |  | * |  | * |  | * |  | * |
| Submission of Reports to the Government |  |  |  |  |  | * |  |  |  |  | * |  |

General Points:

- Monthly  Action  plan indicated in number, do not represent calendar months.  First month will be the month of the Sanctioning of the project.

- The team of the organizers will conduct the meetings every day evenings at the communities in their respective mandals.  In a month they cover 22 to 25 villages.

- Week long Caravan will be in the form of Foot marches & Cycle rallies as mentioned in the above months.  The 50% of Yatris will be local youth and the remaining will be other mandals of the district in order to help the yatris to learn and also visit the works spots of the labourers to sensitize them about the rules and regulations.   Data will be collected there and then about the functioning of the activity.

- The trained cultural troops will visit the areas to perform in different villages not only in their mandal and also at neighboring place. The same youth will be given training and different issues including the right information, how to conduct the social audit etc.,

- The Various tasks force groups will be formed at the mandal level from among beneficiaries, so that they will be able to involve in successful implementation of the project.

BUDGET:

| Sl.No. | Particulars | UNIT | RATE | QTY | PERIOD | TOTAL(Rs) |
| --- | --- | --- | --- | --- | --- | --- |
| I | Education and People's Advocacy |  |  |  |  |  |
| 1 | Pamphlets and educational materials | LPSM | 0.5 | 5000 | 1 | 2,500 |
| 2 | Youth volunteers Training on NREGA for 4 days | PSNL | 120 | 30 | 4 | 14,400 |
|  | Travel for the Trainees | PSNL | 50 | 30 | 1 | 1,500 |
| 3 | Cultural Training Programme: Food and accommodation | PSNL | 100 | 25 | 5 | 12,500 |
|  | Resource persons travel and fees for Cultural Training - 5 days | PSNL | 2500 | 2 | 1 | 5,000 |
|  | Travel for Trainees | PSNL | 50 | 25 | 1 | 1,250 |
| 4 | Week days caravan | LPSM | 10000 | 1 | 1 | 10,000 |
| 5 | Public Hearings in the mandal | LPSM | 10000 | 1 | 1 | 10,000 |
| 6 | Social Audit at mandal | LPSM | 10000 | 1 | 1 | 10,000 |
| II | Project Facilitation |  |  |  |  |  |
| 7 | Salary and Travel for Organizer | PSNL | 3750 | 1 | 12 | 45,000 |
|  | Total (Rs.) |  |  |  |  | 112150 |
|  | Total in USD calculated @ 39 |  |  |  |  | 2875.6 |
|  | Minimum Administration Cost |  |  |  |  | $ 125 |
|  | Grand Total |  |  |  |  | $ 3000 |

This is the budget calculated for a mandal with the inclusion of bare minimum administration which is not included the travel of coordinator. When the more number of mandals are supported, some more budget need to be incorporated to cover the travels of the coordinator to supervise the work.

We request ASHA to find resources for this program from different CHAPTERS selecting one mandal for each CHAPTER.

Submitted by,

### P. Suria Rajini

Executive Director.