# FOR EDUCATION

Asha for Education Silicon Valley Chapter P.O. Box 641741 San Jose, CA 95164-1741

PROJECT HALF YEARLY REPORT

NAME OF ORGANIZATION:    Asha Hyderabad/ BHUMI

Phone-9885419012

Email: asha-hyd@yahoogroups.com

rakesh.dubbudu@gmail.com

NAME OF PROJECT COMPONENT:  Bala Vikas (kosgi)

PERIOD OF REPORT:		1st July 2007		to 31st December  2007

PROJECT CONTACT:	Name: Rakesh Dubbudu

PROJECT STEWARD:	Name: Mr.Surya Potharaju / Mr. Ravi Anantha

I	PROJECT MANAGEMENT

- OVERALL PROGRAMME OBJECTIVE: Mission Statement

To improve school infrastructure, increasing literacy rate by providing quality education and possible by  intensive training and adopting innovative techniques.

- PROJECT PURPOSE: Specific goal of project

To develop various skill-sets in these children with the ultimate aim of gainful employment   and simultaneously improve Public school infrastructure with special emphasis on Quality of Teaching.

- STAFF PARTICULARS:

(Teachers and other staff particulars indicating their qualifications and requirements of additional staff if any.)

All the schools chosen are Govt schools. Bhumi runs schools it has adopted in Hyderabad. The plan is to help Bhumi monitor the progress and slowly take over the adoption of schools with Asha-SV’s support.

There are 46 schools in the Kosgi mandal. The initial request from the MEO was to adopt all these schools for a period of 5years and improve infrastructure in all of them, which was not very pragmatic. During a discussion at the MEOs office we told them to give us the schools that are in urgent need of infrastructure improvements. The 10 schools have been chosen with that in mind. These 10 schools are the ones with primary schools in Thandas (tribal hamlets), middle schools in small villages and one High school which is about 10 kms from Kosgi (mandal HQ). These schools are the ones where roofs are ready to fall, toilets, drinking water and compound walls are immediate needs. The MEO was also careful as he chose the schools where the teaching staff had shown consistent performance to sort of reward their efforts and provide an incentive to other schools

Following are schools chosen to support:

- ZPHS Gundmal

- PS Appayapalli Tanda

- PS Mamidikuntla Tanda

- GPS Gundmal

- UPS Gundmal

- UPS Bogaram

- PS Aminkuntla

- PS Baktimalla

- PS Mudireddi palli

10. Urdumedium Gundmal

- FUNDS RAISED (OTHER THAN ASHA SUPPORT-JULY-DEC.07)

None

- DECISIONS OF EXECUTIVE COMMITTEE IMPACTING SHORT-TERM GOALS:

- Bhumi Conducted a goal setting work shop for the students who are appearing for 10th board exams, which impacted their way of taking exams.

- Uniforms and Low cost Science Kits were distributed to all the schools part of this project. This brought an immediate change in the students interest in learning.

- CURRICULUM UPDATE; TRAININGS CONDUCTED; SPECIAL CLASSES DURING THE PERIOD.

On  Dec 2nd ,2007  a training workshop was conducted for all the science teachers of the participating schools. The trainer was a core volunteer of AID Hyderabad who has good experience in developing low-cost and effective science kits. Provided Science kits for each school, impacting their way of understanding labs;

- REMARKABLE ACHIEVEMENTS (TEACHERS/STUDENTS/COMMITTEE MEMBERS):

One of the major issues was the issue of class among the children. This was visibly seen in the kind of clothes they wore to come to school. This brew the inferiority complex of the poor children. As an immediate step to address this issue, Uniforms were distributed to all the students. May children(Tribal area) were not having proper clothes, now they have school uniform with all students.

- ANY OTHER SUBJECT :

Lot of requests were there to support talented students  from this area(other schools) who cannot afford their schooling cost, we working out a plan to support children’s from this area(Mondal/district) by conducting a talent exam, if they qualified we can support their education expenses, estimation of cost per student, and procedure to identify eligible students is in progress, once we get some solid plan we will update.

9.  IMPLEMENTATION SCHEDULE

| Sr. No. | ACTIVITIES | Apr 08 | May 08 | Jun 08 | Jul 08 | Aug 08 | Sep 08 | Oct 08 | Nov 08 | Dec 08 | Jan 08 | Feb08 | Mar08 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Project Plan |  |  |  | √ | √ | √ |  |  |  |  |  |  |
| 2 | Filed Visits |  |  |  |  |  |  | √ | √ |  |  |  |  |
| 3 | Training workshop for Science Teachers |  |  |  |  |  |  |  |  | √ |  |  |  |
| 4 | Uniform and Science Kit distribution |  |  |  |  |  |  |  |  |  |  |  | √ |
| 5 | Goal Setting workshop for 9th and 10th class students |  |  |  |  |  |  |  |  |  |  |  | √ |
| 6 | Notebooks and Stationery |  |  |  | √ |  |  |  |  |  |  |  |  |
| 7 | Teaching Aids & Games Material |  |  |  |  | √ |  |  |  |  |  |  |  |
| 8 | Benches,Chairs and Almaras |  |  |  |  | V | √ |  |  |  |  |  |  |
| 9 | Toilets and water Facility |  |  |  |  |  |  |  | √ | √ |  |  |  |

# PROJECT WORKPLAN

| Activity 1 and how this was carried out: Training Science teachers on the use of science kits No of beneficiaries: 10 SKILLS: Training |
| --- |
| How the progress was measured | Frequency at which progress was measured and by whom | Results Qualitative Quantitative |
| The teachers were made to demonstrate an experiment after the training session | The progress was measured on the day of the training and subsequent use of the kits. | Before Teachers did not have enough real world examples to demonstrate the science behind issues | After Teachers now have gained insights into how daily activities can be incorporated into teaching science. | Before Teachers did not have enough material to demonstrate the various laws of science | After Teachers now have enough material to demonstrate the various laws of science |

| Activity 2 and how this was carried out: Uniform and Science kit distribution No. of beneficiaries: 1500 + students |
| --- |
| How the progress was measured | Frequency at which progress was measured and by whom | Results Qualitative Quantitative |
| The attendance percentages in the schools prior to and after Uniform distribution. Students show a keen interest in science after seeing the real life examples of laws of science | Every month | Before Children were very apprehensive about coming to school because of the clothes they wore | After Children now have a uniform and they feel to be among equals without any class differences | Before Children were not able to relate the science lessons with real life scenarios | After Children are now not only relate real life scenarios, but demonstrate the experiments |

| Activity 3 and how this was carried out: Goal Setting workshop for 9th and 10th class students by dept of Psychology, Osmania University Skills imparted: Understanding Goals, achieving them No. of beneficiaries—100 children |
| --- |
| How the progress was measured | Frequency at which progress was measured & by whom | Results Qualitative Quantitative |
| The students were able to tell what goals meant and how to set oneself SMART goals | This was done before and after the workshop when the students were asked to speak on goals. | Before Children did not know what SMART goals meant and how important it is to set them | After Children can understand the meaning of SMART goals and understanding ones capability | Before Children were Not able to estimate and understand their capabilities | After Children can now realistically set goals and the also can identify the path and hard work needed to achieve those goals |

Impact Assessment: (Student Achievements)

We illustrate the impact assessment with a case study as below:-

Case Study : There was a marked difference in the way 10th class students expressed themselves before and after the goal setting workshop. They were now able to understand what goals mean and their importance in life, how one needs to set SMART goals. They also understood the means to achieve them are not easy and one needs to work hard to achieve the same.

(Bhumi & Asha Hyd)

Executive Director.