Olcott Memorial High School-  GRR Expenses April to September 2008

| Area-1 | Existing | Requirements | What needs to be done | Estimated Costs of different items | Grant Utilization so far | Expenses in INR |
| --- | --- | --- | --- | --- | --- | --- |
| Improvements to the counseling room | A room 20’ by 14’, with electricity connection. The room is dark and unattractive. There are cement blocks with holes instead of windows. One tube light and two fans | The room needs better ventilation and rodent and protection from insects. | Replace the holed cement blocks with windows and provide meshing against rodents and insects. | Windows and meshing INR50000 (USD1300) | Plans drawn up- May not be able to do the needful within the estimated cost. So for the present another room has been allotted | 0 |
|  |  | Make the room attractive | Painting the walls with good quality light coloured paint | INR6000 (USD150) | Painting the walls and adding mats and some curtains at the cost of Rs2500 | 2500 |
|  |  | Improved lighting | Add three more tube light fittings | INR1000 (USD30) | Not required for the present room. Will be taken up when the other bigger resource room work is taken up. | 0 |
|  | A good writing board, flip chart board. | Scribble areas | On one side of the wall – 2.5’ from the ground and 3’ wide and 20’ long- good writing metal board which can be used as a magnetic display board as well. | INR20000 (USD520) | Flip and chart boards have been bought at the cost of Rs4000 approx. | 4000 |
|  |  | Anger outlet and management corner | Soft corner for punching- punching bags - | INR10000 (USD250) | Materials have been bought for Rs10000. Some more soft toys have been ordered from an innovative soft toys maker. Rs 20,000. Will need to reallocate money in the previous head for this purpose. | 10000 |
|  | Allocation for materials and computers | 3 computers and acessories | Funds available from technology grant recently received by the school | Nil | The students have started using the resources in the new computer room. The room has 10 new computers and 5 more are being added soon. | 0 |

| Area-2 | Existing | Requirements | What needs to be done | Estimated Costs of different items | Grant Utilization so far | Expenses in INR |
| --- | --- | --- | --- | --- | --- | --- |
| Diagnostics for disabilities certification and IEP programmes | Knowledge of places where these can be done at subsidized rates and experience with small numbers | Payments for the centers of assessments. Conveyance costs for students and accompanying adults for various sittings | Provision for 40 children (7% of the student population) Assessment costs Rs400 per child | 40*INR500= INR20,000 (USD 525) | More than 15 students have been taken to MDA for assessment. MDA has not charged for diagnostics. They have helped find remedial teachers for the differently abled students for two days a week on a conveyance paid basis. Rs200 per session for 4 children in 2 batches (8 in all), twice a week One support teacher for classes 1and 2 for English has also been found. We are looking for at least a couple of more support persons. Money spent so far Rs 4000 | 4000 |
|  |  |  | Provision for Conveyance costs Rs100 per child |  | Money spent so far is Rs240 | 240 |
| Area-3 | Existing | Requirements | What needs to be done | Estimated Costs of different items | Grant Utilization so far |  |
| Skills training and apprenticeship location for slow learners | Craft section | Costs for exploration and also trials for the children for the first year- 15 students (2.5% of the student population | Conveyance costs for exploration | 15* INR300= INR 4500 (USD120) | We are still scouting around for such persons. Money spent so far is very small | 0 |
|  |  |  | Conveyance costs for apprentice students | 15*INR1000= INR15000 (USD400) |  |  |
| Area-4 | Existing | Requirements | What needs to be done | Estimated Costs of different items | Grant Utilization so far |  |
| Outreach into community through parents | None | Once a month for 10 months in a year | One meeting a month in an area by rotation | 10*INR1000= INR10000 (USD 260) | Rs1800 at Chemmencheri | 1800 |