Project proposal

1. The title

Water, health and education for women and children of Thar

2. Location

6 villages of Osian block in the Thar Desert

3. Duration

Two years

4. Target population

Nearly 1,800 women and children living in the project villages

5. Background

Western Rajasthan geographically falls in the arid region of India. With a population of 23 million people it is notably the most densely populated arid regions of the world. The average annual rainfall of the area is 100-200 mm (4 to 8 inches). The rural population of the area is dependent largely on rain fed agriculture for its livelihood. However, with recurrent failures of rains and subsequent crop failures, drought has become a chronic feature of the area. There is acute shortage of drinking water as a result of which the community also suffers from serious heath threats, poor sanitation, poverty and other complicated socio- economic problems.

Socially, the biggest impact of lack of water could be seen on the female population and on children of the region. Procuring water is considered to be a household task, and it is the women and the girl child who are involved in procuring water. For this purpose they need to walk miles everyday in the hot and harsh climate. It is also this reason which is responsible to a large extent in the deprivation of the girl child from education. Lack of water and frequent droughts present major challenges in the region and impact the socio-economic status of the region severely. Further, the dry conditions and lack of water pose severe health challenges particularly impacting women and children. In a recent health analysis conducted by the Independent Commission on Development and Health in India and Voluntary Health Association of India, major Indian states have been surveyed and accordingly the districts of the states are classified under a different Vulnerable Health Index (VHI). Almost all the districts of Rajasthan State and all the 12 districts of the Thar Desert were found “very vulnerable” in the above analysis”.

GRAVIS has been focusing in the areas of drought mitigation and improving the living conditions of women and children in the region for a number of years. Over last two decades, it has done commendable work in many villages in developing drought preparedness models. The region is quite large though and GRAVIS needs to expand the work further – continuously, and it also realizes the need of brining women into focus of its programmes.

About GRAVIS

GRAVIS was established in 1983 by a group of social activists inspired by the Gandhian philosophy of social service.  It was felt that development and organization of a variety of programes at the village level was necessary in order to offer real solutions to problems faced by the people of the Thar Desert.

GRAVIS now works in over eight hundred villages of Thar desert covering Jodhpur, Jaisalmer and Barmer, Nagaur and Bikaner districts.  The organization follows an integrated approach focusing on sustainable developmental programmes for alternative rural reconstruction and also mobilizes emergency relief in times of crisis.  The primary approach is aimed at working directly on social rehabilitation and not just monetary assistance thus promoting self-reliance in village communities.

6. Need of the proposed project

GRAVIS efforts focusing on water security, healthcare and education have benefited the rural communities to a very good extent over the last 24 years. However, the region is vast and GRAVIS enters new villages every year to expand the coverage of its work. The proposed project will aim on benefiting six new villages, which have not been covered by GRAVIS’ activities in the past. The activities of the project will focus on ensuring water security, better healthcare and education.

7. Objectives

- Initiate the process of community development in six villages of the Thar Desert

- Organize women through formation of Self Help Groups

- Ensure water security in project villages by construction of water storage tanks

- Improve health conditions of women and children through health education and provision of health services

- Spread literacy among children with a special focus on girl children

8. Proposed activities

Baseline survey of project villages

In the beginning, the project villages will be surveyed by the project team, which will assist in getting the baseline picture of the area. PRA meetings will also be organized along with the base line survey. The findings of base-line survey will be compared with the outcomes of the project at its completion to gauze the impact/change.

Formation of Self Help Groups

Women will be the center of the project. Therefore, the control of the project at the village level will be in the hands of women. Self Help Groups (SHGs) of women will be formed in all project villages. These 10-to-15-member-groups will not only set up their own funds, but will also play important roles in planning, implementation and monitoring of project activities.

SHG members will meet once in a month to discuss the progress of the project. The project will also organize several skill building workshops for the SHGs.

The SHGs will also set up their own small-scale, income-generating units with the help of funds generated by them and through the vocational trainings provided to them by the project team.

GRAVIS has been facilitating the formation of SHGs over 7 years now and has successfully formed over 400 SHGs till date.

Construction of water storage tanks (taankas)

A taanka is an underground tank for harvesting rainwater as well as storing water. It is a traditional method of water storage in dry areas. It taps and stores rain water from a local catchment- natural or artificial. When the stored water is exhausted, the taanka is used to store water transported from outside on cattle carts/ tractors. Thus taanka is an important element of water security in arid regions of Thar. Most importantly, it provides great relief to the women and girls from everyday-water-fetching-drudgery.

Under the project, GRAVIS intends to build eighteen taankas in the six villages. These will benefit 18 poor households comprising of nearly 150 people.

Organization of ANC, immunization and medical camps

The GRAVIS medical team, consisting of a doctor, paramedical staff and village health workers will provide health services during special outreach medical camps in the project villages. The camps will provide ANC services to women and immunization to women and children. These camps will also cater to the general population. These will include screening, treatment of minor ailments, referral to health centers and follow-up of the persons treated earlier etc. During these camps, the health team will also conduct health and hygiene awareness sessions for the community members.

It is proposed to organize 12 medical camps under the project benefiting nearly 600 people.

Setting up schools for children

Lack of educational facilities in a number of Thar Desert villages still is a big challenge. Under the project, GRAVIS aims to set up two schools in remote areas of the project villages. The schools will be set up at community places and the project will provide the support in the form of teachers’ salaries and teaching materials. It is hoped that the construction part of schools will take place later with the support of other donors. Also, the recurring expenses of schools will be born by local community after the project is completed. These two schools will aim on enrolling 100 children in its first year. The number of children will increase gradually in the schools every year.

Project evaluation

The project team in collaboration with the SHGs formed under the project will study the impact of the project through a simple evaluation. The findings of the base-line survey will be compared with the outcomes. The report of the evaluation will be shared with major stakeholders including PPI.

9. Expected outcomes

- Formation of at least 12 strong SHGs which will lead the project initiatives further after the project is completed

- At least 6 income-generating units set up by SHGs

- 18 taankas providing year-long water security to over 150 people

- Improved status of health of the population through provision of medical services to 600 people and through health education among the community.

- Two schools set up providing education to 100 children with at least 50% students being girls

9. Implementation arrangements, monitoring and reporting

The project team will comprise of 1 project coordinator and 1 field worker. In addition, a program coordinator from GRAVIS office will be given the responsibility of implementation, monitoring and reporting of the project.

Monitoring of the project will be done by means of a Performance Indicator Tracking Table (PITT) which will ensure the timely completion of the activities. Along with this GRAVIS will prepare half yearly updates and annual reports of the project.

Monitoring will also be done by the SHGs at their own level, with the GRAVIS team.

10.  Sustainability and Replication

The activities of the project focus on water, health and education which are the basic needs of the region. Therefore, the community will actively participate in the project.   All the interventions of the project are locally suitable, simple and cost effective. With proper care and maintenance, the structures and initiatives can be sustained as functional over the long run.  Members of Self Help Groups with enhanced capacities should be able to carry on the project work in future. GRAVIS has adequate experience of working with the community in region and will be able to find good support.

11. Project budget (all figures in Indian Rupees)

| Particulars | Amount |
| --- | --- |
| Salary of a project coordinator (60%) – 3,000 x 24 months | 72,000 |
| Salary of a field worker – 4,000 x 24 months | 96,000 |
| Travel – 2,000 x 24 months | 48,000 |
| Base line survey | 10,000 |
| Capacity building workshops for SHGs – 2 @ 6,000 | 12,000 |
| Vocational trainings for SHGs – 2 @ 6,000 | 12,000 |
| Exposure visit for SHG | 10,000 |
| Construction of taankas – 18 @ 15,000 | 270,000 |
| Organization of ANC, Immunization and Medical camps – 12 @ 6,000 | 72,000 |
| Support to schools – 2 @ 2,500 per month for 24 months | 120,000 |
| Evaluation | 5,000 |
| GRAVIS administration – 2,000 x 24 months | 48,000 |
| Total | 775,000 |

Year 1 budget

| Particulars | Amount |
| --- | --- |
| Salary of a project coordinator (60%) – 3,000 x 12 months | 36,000 |
| Salary of a field worker – 4,000 x 12 months | 48,000 |
| Travel – 2,000 x 12 months | 24,000 |
| Base line survey | 10,000 |
| Capacity building workshops for SHGs – 2 @ 6,000 | 12,000 |
| Vocational trainings for SHGs – 2 @ 6,000 | 12,000 |
| Exposure visit for SHG | 10,000 |
| Construction of taankas – 9 @ 15,000 | 135,000 |
| Organization of ANC, Immunization and Medical camps – 6 @ 6,000 | 36,000 |
| Support to schools – 2 @ 2,500 per month for 12 months | 60,000 |
| GRAVIS administration – 2,000 x 12 months | 24,000 |
| Total | 407,000 |

# Footnotes

According to GRAVIS studies, water-fetching-exertion in the Thar Desert contributes significantly to high prevalence of anemia and Infant and Maternal mortality.

Health for the millions, Voluntary Health Association of India, June 2004